Change Management Plan

Table of Contents

# Scope and Approach

## Purpose and scope

This plan sets out how the operational and process change brought by the Information System is managed, from the Effective Date to handover, and how changes to the System itself are controlled through the warranty period. It is the change management part of the plan evaluated under Category 3 of Section III. Together with the Cybersecurity Risk Management Plan, it forms the Cybersecurity Risk and Change Management Plan referred to in the System Architecture.

Change has three meanings in this Contract, and the plan keeps them apart:

| Meaning | Where it is managed |
| --- | --- |
| Operational and process change: NRB's staff and processes moving to the new facility | Sections 2, 3, 4 and 6 |
| Technical change control: changes to the hardware, software, middleware and security systems, under Section VII clause 1.4.1.2 | Section 5, using the capabilities in System Architecture Section 12.1 |
| Contractual Change: a change to scope, price or time under GCC 39 | Routed under Section 5.1 only |

| Category 3 item | Requested | Where answered |
| --- | --- | --- |
| Purpose, Table 1 | Sequenced activities, resources and transition steps | Sections 4.1 and 6.1 |
|  | Feasibility | Sections 4.2 and 4.3 |
|  | Alignment of operational and process change management | Sections 2.1 and 3.1 |
| 1. Alignment with international frameworks | Change Management Plan mapped to NIST CSF | Sections 1.2 and 1.3 |
|  | Framework Compliance Matrix | Section 1.3 |
|  | Evidence of past implementation | Section 7.3 |
| 2. Risk identification, mitigation and response | Change and transition risks | Section 4.3 |
|  | Compliance and Governance Statement | Sections 3.1 and 7.1 |
| 3. Resources, skills, duration and capacity building | Resource and Skill Matrix | Section 6.1 |
|  | Capacity-Building and Knowledge Transfer Plan | Section 6.2 |
|  | Timeline | Section 4.1 |
|  | Compliance Statement | Section 7.2 |

The cybersecurity items of Category 3 are answered in the Cybersecurity Risk Management Plan, as listed in Cybersecurity Risk Management Plan Section 1.1. The process designs, the transition mechanics and the training are set out in the Preliminary Project Plan Sections 2 and 3, and this plan refers to them rather than repeating them.

## Frameworks and method

Prosci ADKAR structures the people side of the change: each person affected moves through awareness, desire, knowledge, ability and reinforcement, and each stage is reached through an activity already in the schedule.

| Stage | How it is achieved on this project | Evidence |
| --- | --- | --- |
| Awareness | Walkthroughs of current production and dispatch with the staff who perform each step, weeks 1 to 4; design review with NRB, weeks 5 and 6; factory acceptance delegation, week 17 | Discovery Report; Detailed Design Approval |
| Desire | Procedures written with NRB staff; NRB trainers drawn from NRB's own staff; NRB leadership involved through the Project Steering Committee and the management training in week 26 | Approved procedures; trainer nominations |
| Knowledge | Shadowing from week 15; formal training in weeks 25 to 28 | Training reports; competence matrix |
| Ability | Pilot production run by the trainees in week 26; coaching in live production in weeks 27 and 28 | Pre-commissioning test 15; operational acceptance test 13 |
| Reinforcement | Operational independence shown in week 28; daily review with NRB during stabilization in weeks 31 and 32; monthly service review | Operational acceptance test 16; monthly service report |

ITIL 4 change enablement and ISO/IEC 20000-1:2018 clause 8.5.1 structure the technical change control in Section 5. The practice is aligned with them.

NIST Cybersecurity Framework 2.0 is the structure shared with the Cybersecurity Risk Management Plan, and the change controls are mapped to it in Section 1.3.

## Framework compliance matrix

The matrix covers the change-related categories. The rest of the Framework is mapped in Cybersecurity Risk Management Plan Section 3.2.

| NIST CSF 2.0, with ISO/IEC 27001 and ISO/IEC 20000-1 | How it is met | Evidence |
| --- | --- | --- |
| ID.RA-07 Changes managed and assessed for risk (A.8.32; ISO/IEC 20000-1 clause 8.5.1) | Change types, approval and procedure, Sections 5.1 and 5.2 | Change log; change board minutes |
| PR.PS-01 Configuration management (A.8.9) | Baselines, version control and drift detection, Section 5.3; System Architecture Section 12.1 | Configuration repository; drift reports |
| PR.PS Separation of environments (A.8.31) | Changes promoted from development through user acceptance testing to production, Section 5.2 | Release records |
| GV.RR Roles and responsibilities (A.5.2, A.5.3) | Roles, decision rights and separation of duties, Section 3.1 | Approved governance tables |
| GV.PO Documented operating procedures (A.5.37) | Procedure lifecycle and ownership, Section 2.1 | Approved Standard Operating Procedures |
| PR.AT Awareness and training (A.6.3) | Capacity building, Section 6.2; Preliminary Project Plan Section 3 | Training records; competence matrix |
| ID.IM Improvement (Clause 10) | Review of emergency and failed changes; lessons from pilot production and coaching, Section 5.2 | Review records |

# Changes and Stakeholders

## What changes and how it is aligned with the project

Section VII clause 0.2.2 expects the facility to move national identity card issuance from a potentially manual, less secure and slower process to a modern, secure and efficient one. Today the existing card printers are fed by a middleware application reading the NRIS database, as described in System Architecture Section 13.2. The change is therefore to how NRB's staff receive, produce, account for and dispatch cards, as well as to the equipment they use.

Each process follows the same path. It is designed with NRB and approved in weeks 5 and 6, its procedure is drafted in week 5 and issued in week 24, it is taught in weeks 25 to 28, and it is proven in live operation before NRB takes ownership of it. The process designs are in Preliminary Project Plan Section 2.4.

| Process | What changes for NRB staff | Proven by |
| --- | --- | --- |
| Request intake | Records released in NRIS are retrieved through one gateway, instead of by middleware reading the database. A record that fails validation is held with a reason and reported back to NRIS | Pre-commissioning test 9; operational acceptance test 6 |
| Production | Batches are assigned to either line, with in-line verification and reproduction of rejected cards within the same job | Operational acceptance tests 1, 3 and 7 |
| Card accountability | Every blank is held against its serial number from delivery to issue or certified destruction, and reconciled every shift | Operational acceptance tests 9 and 14 |
| Mailing and dispatch | Cards are matched with their carriers by card identifier, enveloped and batched by ordering office | Operational acceptance test 8 |
| Status | Status is published to NRIS automatically, where it drives the document tracker and the SMS to the cardholder | Operational acceptance tests 6 and 9 |
| Operation and first-line support | NRB staff operate the facility, administer the System and give first-line support | Operational acceptance tests 13 and 16 |

Procedures. The Standard Operating Procedures are drafted with the NRB staff who will use them. They are issued in week 24 so that training teaches from them, then corrected from pilot production in week 26 and from coaching in weeks 27 and 28 under the documentation control of Preliminary Project Plan Section 4.7. They are proven usable in operational acceptance test 16. From handover each procedure has a named NRB process owner, and it changes only through documentation control, and through Section 5 where the change also touches the System.

## Stakeholders, impact and communication

The numbers of staff are those recommended in Preliminary Project Plan Section 3.2.

| Group | What changes for them | How they are engaged | Ready when |
| --- | --- | --- | --- |
| User roles: operators, mailing and dispatch officers, quality assurance staff, card issuance officers, supervisors and helpdesk, 24 | New consoles, procedures and controls across two shifts | Discovery walkthroughs; pilot production in week 26; training in weeks 25 to 28; coaching in weeks 27 and 28 | Assessed competent; operational acceptance test 13 passed |
| Technical staff, 15 | Administration and first-line support of a new estate | Factory training in week 17; shadowing from week 15; technical training in weeks 26 and 27 | Operational acceptance test 16 passed |
| Management, 9 | Oversight of a new facility, its controls and its approvals | Project Steering Committee; design review; management training in week 26 | Readiness decisions taken at each gate in Section 4.2 |
| Staff of the existing printing operation | Their process moves to the new facility at cutover | Discovery walkthroughs; briefing before cutover. Their nomination as trainees is NRB's decision | NRB's cutover decision |
| NRB developers | Build the NRIS side of the interface, which replaces the middleware | Interface Control Documents; joint checkpoint every two weeks from week 7; user acceptance testing in weeks 24 and 25 | Integration complete |
| e-Government | Issues the certificates and provisions the network and remote access | Working sessions during design; inputs dated in Preliminary Project Plan Section 2.7 | Inputs delivered on their dates |
| Registration and ordering offices | Cards arrive batched by ordering office, with their status in the document tracker | Through NRB | NRB's announcement of live production |

Communication. NRB leads communication with its own staff, with the registration and ordering offices and with the public, and decides when live production is announced. Inkript provides the content and briefings NRB needs, and takes part in stakeholder engagement when asked, under GCC 9.13. Inkript keeps NRB management and the NRIS team informed through the project bodies in Section 3.1, and makes no public statement.

# Governance

## Roles, decisions and reporting

The plan uses the project bodies that already exist, and adds only a change board for technical change.

| Role or body | Responsibility |
| --- | --- |
| Project Steering Committee | Receives the change and readiness status monthly; decides any readiness gate referred to it |
| Purchaser's Project Manager | Approves the processes, procedures and readiness at each gate |
| Supplier's Representative | Coordinates the Supplier's work and reports monthly |
| Training and Change Management Specialist | Owns this plan: impact on each group, support to NRB's engagement, procedure adoption, and the readiness evidence for each gate |
| Change board | Solution Architect as Supplier technical lead, NRB ICT manager, NRB operations manager, and the NRB security officer for security-relevant changes. Approves technical changes under Section 5. Meets weekly from the start of installation in week 15, and monthly or on demand in operation. Chaired by NRB from handover |
| NRB process owners | Own each process and its procedures from handover |

| Decision | Decided by |
| --- | --- |
| Approval of processes, roles and procedures | Purchaser's Project Manager |
| Timing of cutover, for each request type | NRB |
| Readiness at each gate | Purchaser's Project Manager, on the Steering Committee's recommendation |
| Normal technical change | Change board |
| Emergency technical change | Incident manager or NRB ICT manager, and reviewed at the next change board |
| Change to scope, price or time | The Purchaser, by Change Order under GCC 39 |
| Withdrawal of the existing card printers | NRB, after operational acceptance test 2 |

Separation of duties. No one approves a change they requested or implement, developers do not deploy to production, and the operator who runs a job is not the supervisor who releases it.

Reporting. Change and readiness status is part of the Monthly Progress Report under GCC 19.5, including the actions expected from NRB in the next period. Training reports are issued under SCC 19.6(b), and the Change Order Log is kept with the progress reports. From handover, adoption issues and changes made in the period are reported in the monthly service report of Preliminary Project Plan Section 5.6. No other report is added.

# Transition and Readiness

## Transition sequence

The change activities run within the ten phases and contractual milestones of Preliminary Project Plan Section 2.1, on the dates already set there. This plan adds no date of its own.

| Phase and weeks | Change activities | Condition |
| --- | --- | --- |
| Mobilization and planning, weeks 1 to 2 | Plan baselined in the Project Initiation Document; recommended trainee numbers and prerequisites issued to NRB; discovery walkthroughs begin |  |
| Design and detailed planning, weeks 3 to 6 | Walkthroughs of current production and dispatch with the staff who perform them; Discovery Report in week 4; future-state processes, roles and draft procedures in week 5; design review with NRB | Detailed Design Approval: processes, roles and separation of duties approved |
| Procurement and manufacturing, weeks 7 to 16 | Joint checkpoints with NRB developers every two weeks; factory acceptance delegation nominated by week 12; technical trainees nominated and shadowing from week 15 |  |
| Factory acceptance testing, week 17 | Equipment training of the NRB delegation at the factory | Successful FAT |
| Installation and site acceptance testing, weeks 21 to 26, with the ICT from week 15 | User trainees nominated by week 20; procedures, manuals and training materials issued in week 24; user acceptance testing with NRIS stakeholders in weeks 24 and 25; pilot production run by the trainees in week 26, its cards not issued | Installation and SAT: the readiness gate in Section 4.2 |
| Training and knowledge transfer, weeks 25 to 28 | User training groups in weeks 25 and 26; management training in week 26; technical training in weeks 26 and 27; cover group trained by NRB trainers in weeks 27 and 28 | Training completed: competence matrix delivered |
| Commissioning, weeks 27 to 30 | Live production begins with the operational acceptance tests, on NRB's cutover decision for each request type; coaching in production; operational independence in week 28; final acceptance demonstration in weeks 29 and 30 | System commissioned |
| Handover and go-live, weeks 31 to 32 | Stabilization with resident engineers on every shift and a daily review with NRB; process ownership and change control transferred to NRB | Full handover and go-live |

The resources for each activity are the roles in Section 6.1 and the NRB staff in Section 2.2. The schedule is the one shown in Preliminary Project Plan Section 2.2.

## Readiness gates and fallback

People and process readiness is checked at the gates the project already has, and each gate has a defined outcome if readiness is not met.

| Gate and week | Readiness required | If not met |
| --- | --- | --- |
| Detailed Design Approval, week 6 | Future-state processes, roles and separation of duties approved | Corrected before approval, not carried into the build |
| Successful FAT, week 17 | NRB delegation trained on the equipment | Equipment training completed on site during installation |
| Installation and SAT, week 26 | Procedures issued; pilot production passes pre-commissioning test 15; both shifts staffed by trainees | Live production does not start. Requests stay in NRIS and the existing printers continue |
| Start of live production, week 27 | NRB's cutover decision for each request type | That request type stays on the existing printers |
| Operational independence, week 28 | Operational acceptance tests 13 and 16 passed | Tasks retrained and the tests repeated before the final demonstration |
| System commissioned, week 30 | Final acceptance demonstration passed; manuals proven usable | Corrected and the test repeated |
| Full handover, week 32 | NRB holds process ownership and the change-control roles in Section 3.1 |  |

Fallback. Issuance does not depend on the new facility until it is proven. A request is produced by one facility only, the existing printers remain available until operational acceptance test 2 has passed, and a request not yet produced stays in NRIS, so a pause delays cards without losing them. These arrangements are set out in Preliminary Project Plan Section 2.6.

## Feasibility and transition risks

Why the transition is feasible.

- Every input from NRB that the transition depends on, from trainee nominations to the cutover decision, is dated in Preliminary Project Plan Section 2.7 and followed in the monthly report.

- Training has no float, and the plan is built around it: operators are trained first, so that both shifts can run production from week 27.

- Responsibility moves to NRB in stages, and each stage has a condition that must be met before the next, as set out in Preliminary Project Plan Section 3.1.

- The fallback in Section 4.2 keeps card issuance running whatever happens to the new facility during acceptance.

Transition risks. Rated on the scale of the project risk register in Preliminary Project Plan Section 2.9. R10 and R11 are in that register; R13 and R14 are added by this plan.

| Risk | Rating | Mitigation | Owner |
| --- | --- | --- | --- |
| R10 A request is produced by both the existing printers and the new facility during transition | Low likelihood, high impact | Release to the new facility marked in NRIS and excluded from the middleware selection; tested in pilot production | NRB, with Inkript |
| R11 Trained NRB staff are not available in the numbers needed for operational independence | Medium likelihood, medium impact | Recommended numbers issued in week 2; nominations by week 20; operators trained first | NRB, with Inkript |
| R13 Staff return to former practice, or work around the new controls, once the Supplier steps back | Medium likelihood, medium impact | Procedures written with the staff who use them; NRB trainers; operational acceptance tests 13 and 16; daily review during stabilization; adoption issues in the monthly service review | NRB operations manager, with Inkript |
| R14 An unapproved or faulty change stops production or weakens a control | Low likelihood, high impact | Change procedure in Section 5.2; drift detection; changes outside the production day; rollback plan for every change; requirements freeze | Change board |

The risk that NRB cannot operate the security controls after handover is C15 in Cybersecurity Risk Management Plan Section 4.3.

# Technical Change Control

## Change types and approval

Change control covers every component named in Section VII clause 1.4.1.2: the hardware, the software, the middleware and the security systems, including equipment firmware and the manufacturer's releases, the NRIS interfaces, the card layout templates, the firewalls, the security monitoring and the hardware security modules. The physical security installations are under the facility works, and only their integration with monitoring falls under this control. The capabilities that support it are described in System Architecture Section 12.1.

| Type | Examples | Approved by, and when applied |
| --- | --- | --- |
| Standard | Pre-approved, repeatable changes such as the monthly patch cycle | The change board approves the model once; applied in a maintenance window |
| Normal | Software releases, configuration changes, firmware, interface definitions, card layout templates, new versions from manufacturers | The change board, after testing outside production; applied in a maintenance window |
| Emergency | Critical security patches applied out of cycle, and changes needed during an incident or recovery | The incident manager or the NRB ICT manager; reviewed at the next change board |
| Change to scope, price or time | A change to what the Contract requires | The Purchaser, by Change Order under GCC 39, recorded in the Change Order Log; then delivered as a normal change |

The Change Order Log, which records contractual Changes, is kept apart from the technical change log. Patching follows the cycle in Cybersecurity Risk Management Plan Section 6.3.

## Change procedure

| Step | What is done and recorded |
| --- | --- |
| Request | The change is logged in the configuration repository with its reason and requester |
| Impact analysis | The components, interfaces, environments and security controls affected are identified, and a rollback plan is written |
| Approval | By the authority for its type in Section 5.1. The approver is neither the requester nor the implementer |
| Scheduling | Placed in a maintenance window in the production calendar agreed with NRB |
| Implementation | Promoted from development through user acceptance testing to production, with the training environment kept at the same version. Developers do not deploy to production |
| Verification | The change is checked against its expected result and reconciled with the audit log |
| Closure | The configuration baseline is updated. Emergency and failed changes are reviewed, and the lessons recorded |

Maintenance windows. Changes are made outside the production day of two seven-hour shifts. Paired components are changed one at a time while the other carries the load, and equipment one line at a time while the other line produces, as described in System Architecture Section 11.5.

Drift. When drift detection finds a configuration that differs from its baseline, the difference is investigated. It is either reversed, or approved as a change after the event. A difference that cannot be explained is treated as a security event.

## Lifecycle and handover of change control

| Period | How change is controlled |
| --- | --- |
| Design to installation, weeks 6 to 26 | Approved documents are changed only with the Project Manager's approval, under GCC 21.3.7. Builds and configurations are versioned, and every departure from the approved design is recorded for the as-built documentation |
| Requirements freeze | Under GCC 39.1.5, the date after which the Technical Requirements are frozen is proposed at the Installation Certificate in week 26 and agreed in the Project Plan. A Change raised later is dealt with after Operational Acceptance, except defect corrections and emergency changes |
| Commissioning, weeks 27 to 30 | The accepted configuration is the baseline, as set out in Preliminary Project Plan Section 4.7, and changes pass only through Section 5.2 |
| Handover, weeks 31 to 32 | The final configuration baselines are delivered in the as-built documentation. NRB takes the approver roles and chairs the change board. Supplier access is reduced to named support accounts used with NRB's approval |
| Warranty | Defect corrections and new versions are delivered as normal changes. Modifications go first through the Contract's change procedure, then through change control |

NRB's administrators and managers are trained for these roles in the software administration module and the governance and operations module of the Training Sub-Plan, Preliminary Project Plan Sections 3.4 and 3.5.

# Resources and Capacity Building

## Resource and skill matrix

| Role | Change responsibilities and engagement |
| --- | --- |
| Training and Change Management Specialist | Owns this plan: impact on each group, support to NRB's engagement, procedure adoption, readiness evidence at each gate, and reinforcement after go-live. Also leads the training program, as in Preliminary Project Plan Section 3.8. Weeks 1 to 32, on site from week 15 |
| Supplier's Representative | Coordination with the Purchaser's Project Manager; Monthly Progress Report |
| Solution Architect | Impact analysis of technical changes; Supplier technical lead on the change board until handover |
| Software Integration Specialist | Software releases and interface changes |
| Secure Personalization System Engineer and Card Mailing System Engineer, with the equipment manufacturer | Equipment and firmware changes; content of the procedures for the production and mailing lines |
| Cybersecurity and PKI Specialist | Security impact of changes; incident manager for emergency changes until handover |
| NRB process owners, ICT manager and trainers | Counterparts who take over each process, the change-control roles and the training of new staff |

The Training and Change Management Specialist meets Section VII clause 2.4.1.11: a degree in ICT, education or human resource development, trainer certification, change management certification, Prosci preferred, and at least five years delivering ICT training to government staff, operators and technical administrators. The CV and certificates are provided with the Key Personnel forms.

## Capacity building and knowledge transfer

The staged transfer of responsibility to NRB, from factory training to independent operation, is the knowledge transfer plan of Preliminary Project Plan Section 3.1 and is not repeated here. The change side adds the transfers below.

| What NRB takes over | How | Transfer criterion |
| --- | --- | --- |
| Process and procedure ownership | Procedures written with NRB staff, taught from in training, and corrected in pilot production and coaching | Procedures proven usable in operational acceptance test 16 |
| Change control | NRB administrators and approvers run changes under observation in weeks 27 to 30 | NRB has run a normal change and a rehearsed emergency change end to end, with the Supplier observing |
| Training of new staff | Six NRB trainers are certified after delivering the cover group under observation in weeks 27 and 28 | Trainer certificates |
| Security operations | As set out in Cybersecurity Risk Management Plan Section 9.4 | The transfer criteria there |

Reinforcement. The change is sustained after go-live. Resident engineers review production with NRB every day during stabilization in weeks 31 and 32. Adoption issues are raised in the monthly service review. NRB's trainers train new staff from the same materials. Users are briefed on each new release before it is applied under change control.

# Compliance

## Compliance statement

Inkript confirms that, if awarded the Contract, it will:

- provide the Training and Change Management Specialist required by Section VII clause 2.4.1.11 throughout supply and installation;

- deliver the transition in the sequence and through the readiness gates of Section 4, without moving a contractual milestone;

- operate the change management framework of Section VII clause 1.4.1.2 for all components through the warranty period, as set out in Section 5 and System Architecture Section 12.1;

- support NRB's stakeholder engagement under GCC 9.13;

- route every change to scope, price or time through GCC 39, and keep the Change Order Log;

- agree the requirements freeze date under GCC 39.1.5 in the Project Plan;

- report change and readiness status monthly, as set out in Section 3.1.

## Requirements compliance matrix

| Requirement | Response |
| --- | --- |
| Section VII clause 1.4.1.2, Installation and configuration. Repeatable installation, centralized and version-controlled configuration, secure baselines, deployment across environments | Complies. System Architecture Section 12.1. The environments are development, training, user acceptance testing and production |
| Section VII clause 1.4.1.2, Change management requirements. Role-based approval, logging, separation of duties, emergency changes with review, version control, rollback, impact analysis, scheduling and maintenance windows | Complies. System Architecture Section 12.1; Sections 5.1 and 5.2 |
| Section VII clause 1.4.1.2, Configuration governance. Central repository, audit trail, baselines, compliance enforcement, drift detection | Complies. System Architecture Section 12.1; Sections 5.2 and 5.3 |
| Section VII clause 1.5.2.6. Maintenance windows with minimal downtime | Complies. System Architecture Section 11.5; Section 5.2 |
| Section VII clause 2.4.1.11. Training and Change Management Specialist | Complies. Section 6.1 |
| Section VII clause 2.2. On-the-job operational coaching; shadow support during commissioning | Complies. Preliminary Project Plan Section 3.1 |
| Operational acceptance tests 13, 16 and 17. Multi-shift operation, operational independence, final acceptance demonstration | Complies. Section 4.2; Preliminary Project Plan Section 4.6 |
| GCC 9.13. Stakeholder engagement | Complies. Section 2.2 |
| GCC 39.1.5. Requirements freeze | Complies. Section 5.3 |

## Evidence of past implementation

Attached to the Technical Proposal. The CV and certificates of the Training and Change Management Specialist, including the change management certification.

Past implementation. [Inkript to complete with two or three references and attach the client letters. The references in Cybersecurity Risk Management Plan Section 11.3 may be used, described here by their transition and change scope.]

| Project, client, country and period | Transition and change scope comparable to this Contract | Evidence attached |
| --- | --- | --- |
| [Reference 1] | [For example: cutover from a legacy issuance process, operator and administrator training, handover of operation to a government agency, change control in operation] | [Client letter] |
| [Reference 2] |  |  |
| [Reference 3] |  |  |