# JV Responsibility Matrix – Malawi National ID Solution Tender

## Joint Venture Overview

Inkript  (Lead Partner) and RME(Local Partner) submit this bid as a Joint Venture for the design, supply, deployment and support of the National ID Solution for the Government of Malawi. X carries technical and delivery responsibility for the solution; Y carries local execution, site, logistics, commercial and legal responsibility in Malawi.

| Partner | Role | Core scope |
| --- | --- | --- |
| Inkript | Lead Partner (technical) | System design, application, cyber security, supply of printers, servers and cards delivered to Malawi, Level 1–3 support |
| RME | Local Partner (in-country) | Civil works, customs clearance, data centre deployment, end-user coordination, invoicing, legal agreements |

## RACI Legend

| Code | Meaning |
| --- | --- |
| R | Responsible: performs the work |
| A | Accountable: owns the outcome and signs off (one per activity) |
| C | Consulted: provides input before or during the work |
| I | Informed: kept updated on progress and results |

## Responsibility Matrix

Each activity has one accountable partner; the other partner is consulted or informed as shown.

| No. | Phase | Activity | Inkript | RME |
| --- | --- | --- | --- | --- |
| 1 | Project management | Overall JV project management and single point of contact with the Client | A/R | C |
| 2 | Project management | Project plan, schedule and progress reporting | A/R | C |
| 3 | Project management | Coordination with end users and government stakeholders in Malawi | C | A/R |
| 4 | Design | Requirements gathering and needs assessment | A/R | C |
| 5 | Design | Solution and system architecture design | A/R | I |
| 6 | Design | Data centre design specifications (power, cooling, racks, network) | A/R | C |
| 7 | Design | Site surveys and civil works design | C | A/R |
| 8 | Supply | Procurement of card printers, servers and related hardware | A/R | I |
| 9 | Supply | Procurement of ID card blanks and consumables | A/R | I |
| 10 | Supply | International shipping and delivery to Malawi port of entry | A/R | C |
| 11 | Logistics | Customs clearance, import permits and duties handling | C | A/R |
| 12 | Logistics | Inland transport, local storage and delivery to sites | I | A/R |
| 13 | Civil works | Site preparation and civil works (buildings, cabling routes, rooms) | C | A/R |
| 14 | Data centre | Data centre deployment (facility, power, cooling, racks, physical security) | C | A/R |
| 15 | Installation | Installation and configuration of servers and network equipment | A/R | C |
| 16 | Installation | Installation and configuration of card printers and enrolment equipment | A/R | C |
| 17 | Application | Development, customisation and configuration of the ID system application | A/R | I |
| 18 | Application | Data migration and system integration with government systems | A/R | C |
| 19 | Cyber security | Security architecture, hardening and access control | A/R | I |
| 20 | Cyber security | Security testing, vulnerability assessment and compliance | A/R | I |
| 21 | Testing | Factory Acceptance Test (FAT) | A/R | I |
| 22 | Testing | Site Acceptance Test (SAT) and User Acceptance Test (UAT) | A/R | C |
| 23 | Training | End-user and administrator training | A/R | C |
| 24 | Training | Training venues, logistics and trainee coordination | C | A/R |
| 25 | Handover | Documentation, commissioning and go-live | A/R | C |
| 26 | Support | Level 1 support (first-line, on-site user issues) | A/R | C |
| 27 | Support | Level 2 support (local technical troubleshooting) | A/R | C |
| 28 | Support | Level 3 support (remote expert and vendor-level support) | A/R | I |
| 29 | Commercial | Issuance of invoices to the Client | C | A/R |
| 30 | Commercial | Collection of payments and distribution between JV partners | C | A/R |
| 31 | Legal | Contract signing, legal agreements and local registration | C | A/R |
| 32 | Legal | Local tax, licences and statutory compliance | I | A/R |

## Notes :

- JV Lead is RME

- Customer to pay Inkript

- Data center: RME to purchase the facility equipment (UPS, cooling, racks)