Cybersecurity Risk Management Plan

Table of Contents

1. Scope and Approach	3

1.1 Purpose and scope	3

1.2 Frameworks and method	3

2. Governance	5

2.1 Governance and decision rights	5

2.2 Security policies	5

3. Architecture and Framework Compliance	7

3.1 Cybersecurity architecture	7

3.2 Framework compliance matrix	7

4. Risk Assessment	9

4.1 Method	9

4.2 Risk criteria and assessment matrix	9

4.3 Risk identification register	10

4.4 Risk position before and after treatment	11

5. Mitigation and Control Strategy	12

5.1 Control strategy	12

5.2 Controls by risk	12

5.3 Mitigation and control strategy template	13

6. Implementation Method Statement	15

6.1 Security activities by phase	15

6.2 Security testing	15

6.3 Handover and operation	16

7. Incident Response Plan	17

7.1 Team and escalation matrix	17

7.2 Response process	17

7.3 Contractual incident categories	18

7.4 Notification and reporting	19

8. Business Continuity Response Plan	20

8.1 Recovery targets and scenarios	20

8.2 Activation, communication and testing	20

9. Resources, Schedule and Capacity Building	22

9.1 Cybersecurity work breakdown structure	22

9.2 Timeline	23

9.3 Resource and skill matrix	23

9.4 Capacity building and knowledge transfer	24

10. Innovations	26

11. Compliance	27

11.1 Compliance and governance statement	27

11.2 Requirements compliance matrix	27

# Scope and Approach

## Purpose and scope

This plan sets out the method statement, management strategies, implementation plans and innovations by which the cyber security risks of the Information System are managed, as required by PDS ITP 11.2(j), and is the cybersecurity risk part of the plan evaluated under Category 3 of Section III. Together with the Change Management and Configuration Governance Plan, presented separately, it forms the Cybersecurity Risk and Change Management Plan referred to in the System Architecture.

It covers the Information System at the Card Production Facility and in the secondary environment, from the Effective Date through the warranty period. The security controls themselves are described in System Architecture Section 10, and this plan refers to them rather than repeating them.

| Category 3 criterion | Item requested | Where answered |
| --- | --- | --- |
| 1. Alignment with international frameworks | Plan mapped to NIST CSF or ISO 27005 | Sections 1.2, 3 and 4 |
|  | Framework Compliance Matrix | Section 3.2 |
|  | Cybersecurity Architecture Diagram | Section 3.1 |
| 2. Risk identification, mitigation and response | Risk Identification Register | Section 4.3 |
|  | Risk Assessment Matrix | Sections 4.2 and 4.4 |
|  | Mitigation and Control Strategy Document, template | Section 5 |
|  | Incident Response Plan | Section 7 |
|  | Business Continuity Response Plan | Section 8 |
|  | Compliance and Governance Statement | Sections 2 and 11.1 |
| 3. Resources, skills, duration and capacity building | Cybersecurity Work Breakdown Structure | Section 9.1 |
|  | Resource and Skill Matrix | Section 9.3 |
|  | Capacity-Building and Knowledge Transfer Plan | Section 9.4 |
|  | Timeline and Gantt chart | Section 9.2 |
|  | Compliance Statement | Section 11.2 |
| PDS ITP 11.2(j) | Method statement and implementation plans | Sections 6 and 9 |
|  | Management strategies | Sections 2, 4 and 5 |
|  | Innovations | Section 10 |

## Frameworks and method

NIST Cybersecurity Framework 2.0 is the organizing structure. Every control is placed against the six functions, Govern, Identify, Protect, Detect, Respond and Recover, and the compliance matrix in Section 3.2 covers all 22 categories.

ISO/IEC 27005:2022 is the risk management process: criteria, identification, analysis, evaluation, treatment, acceptance, and monitoring and review, in Section 4.

ISO/IEC 27001:2022 provides the management system and the Annex A controls. The information security management system of Inkript, the joint venture member responsible for the Information System, is certified to ISO/IEC 27001, and the certificate is included in the Technical Proposal.

What the plan protects first. The most serious outcome in a card production facility is not data loss alone. It is a genuine card, correctly signed, produced for a person not entitled to it, because no verifier can tell it from a legitimate one. The risk criteria, the register and the detection priorities are weighted accordingly, alongside the protection of citizens' personal and biometric data under the Data Protection Act 2024.

# Governance

## Governance and decision rights

| Role or body | Responsibility |
| --- | --- |
| Project Steering Committee | Receives the security status monthly; decides on any High residual risk referred to it |
| Security Working Group | Supplier security lead, NRB security officer, NRB ICT manager, Solution Architect and Network Engineer. Reviews the risk register, controls, vulnerabilities, incidents and the monthly compliance report, every two weeks during implementation and monthly in operation |
| Supplier security lead | The Cybersecurity and PKI Specialist. Owns this plan, the risk register and the Incident Response Plan; incident manager until handover |
| NRB security officer | Accepts residual risk; incident manager from handover |

| Decision | Decided by |
| --- | --- |
| Approval of the security design and policies | Purchaser's Project Manager |
| Acceptance of a Medium residual risk | NRB security officer |
| Acceptance of a High residual risk, time-bound with a treatment plan | Purchaser's Project Manager |
| Suspension of signing or production on an S1 incident | Incident manager, at once |
| Resumption of signing or production after an S1 incident | NRB, in writing |
| Invocation of the secondary environment | NRB's business continuity manager, on the Supplier's advice |

The Supplier remains the single point of accountability under ITP 16.2(b). Its obligations under GCC 44.1 are flowed down in writing to the equipment manufacturer, the card manufacturer and the facility works subcontractor, according to what each touches.

## Security policies

The System enforces the following policies, as stated in System Architecture Section 10.7. They are drafted during design, approved with it in week 6, and owned by NRB from handover.

| Policy | What it governs | Implemented through |
| --- | --- | --- |
| Information security | Objectives, scope, roles and frameworks | This plan |
| Access control | Role-based access, separation of duties, multi-factor authentication, privileged and just-in-time access, recertification | System Architecture Sections 6.12 and 10.3 |
| Acceptable use | Use of facility systems, removable media and personal devices, handling of citizen data | System Architecture Sections 10.2 and 10.3 |
| Cryptographic key management | Algorithms, key lifecycle, custody of the hardware security modules, certificates | System Architecture Section 10.4 |
| Vulnerability management | Scanning, assessment, penetration testing, remediation by severity | System Architecture Section 10.5 |
| Patch management | Patch cycles, emergency patching, the equipment manufacturer's releases | System Architecture Section 10.5 |
| Logging and monitoring | Log sources, integrity, retention, alerting | System Architecture Sections 10.6 and 10.7 |
| Incident response | Classification, escalation and reporting | Section 7 |

Each policy is reviewed annually and after any S1 incident.

# Architecture and Framework Compliance

## Cybersecurity architecture

The architecture is layered, so that no single control is the only thing standing between an attacker and citizen data or the signing key. It is described in System Architecture Section 10, with the network zones in System Architecture Section 9.2.

Figure 3.1: Cybersecurity architecture, arranged by the six functions of the NIST Cybersecurity Framework 2.0. Protective controls run in depth from the network to the data and keys, with detection, response and recovery spanning every layer. The double border is provided by the Purchaser.

## Framework compliance matrix

| NIST CSF 2.0 category, with ISO/IEC 27001 Annex A | How it is met | Evidence |
| --- | --- | --- |
| GV.OC Organizational context (A.5.31, A.5.34) | Mission, stakeholders and Malawi legal obligations set the risk criteria, Section 4.2 | Compliance statement; Privacy Impact Assessment |
| GV.RM Risk management strategy (Clause 6.1; Clause 8.2) | ISO/IEC 27005 process and acceptance authority, Section 4 | Risk register |
| GV.RR Roles and authorities (A.5.2, A.5.3) | Governance and decision rights, Section 2.1; qualified personnel, Section 9.3 | CVs and certificates |
| GV.PO Policy (A.5.1, A.5.10) | Eight security policies, Section 2.2 | Approved policies |
| GV.OV Oversight (A.5.35, A.5.36) | Security Working Group and monthly compliance report, Section 6.3 | Monthly reports |
| GV.SC Supply chain (A.5.19 to A.5.22) | Obligations flowed down under GCC 44.1; inspection on delivery; factory integrity baseline, Section 6.1 | Delivery and factory records |
| ID.AM Asset management (A.5.9, A.5.12) | Hardware, software, certificate and key inventories; serialized blank stock; data classification, System Architecture Sections 6.10 and 10.2 | Asset register |
| ID.RA Risk assessment (A.5.7, A.8.8) | Risk register; threat modeling at design; vulnerability scanning, Sections 4 and 6.1 | Register; scan reports |
| ID.IM Improvement (A.5.27; Clause 10) | Findings of tests, exercises and incidents fed back into the register and procedures | Post-incident reports |
| PR.AA Identity and access control (A.5.15 to A.5.18, A.8.2, A.8.5) | Single sign-on, multi-factor authentication, privileged and just-in-time access, recertification, System Architecture Section 10.3 | Pre-commissioning test 5; operational acceptance test 10 |
| PR.AT Awareness and training (A.6.3) | Security modules for users, administrators and managers, Section 9.4 | Training records |
| PR.DS Data security (A.8.11, A.8.13, A.8.24) | AES-256 at rest, TLS 1.2 or higher in transit, masking, minimization, encrypted immutable backups, System Architecture Section 10.2 | Encryption validation |
| PR.PS Platform security (A.8.7, A.8.9, A.8.25 to A.8.29) | Hardened CIS baselines, secure boot, patching, endpoint detection, secure development, System Architecture Sections 9.1 and 10.5 | Hardening guide; release gate records |
| PR.IR Infrastructure resilience (A.8.14, A.8.20, A.8.22) | Segregated zones, firewall pair, clustering, secondary environment, System Architecture Sections 9.2 and 9.3 | Pre-commissioning tests 4 and 13 |
| DE.CM Continuous monitoring (A.8.15, A.8.16) | Security information and event management at all hours, behavior analytics, physical events, System Architecture Section 10.7 | Operational acceptance tests 10 and 12 |
| DE.AE Adverse event analysis (A.5.25) | Detection rules derived from the risk register; classification S1 to S4, Sections 7.2 and 10 | Exercise report |
| RS.MA Incident management (A.5.24, A.5.26) | Incident Response Plan and escalation matrix, Section 7 | Approved plan |
| RS.AN Incident analysis (A.5.28) | Evidence preserved with chain of custody, System Architecture Section 10.7 | Evidence log |
| RS.CO Incident reporting (A.5.5, A.6.8) | Notification within 24 hours under SCC 19.7, Section 7.4 | Notification records |
| RS.MI Incident mitigation (A.5.26) | Containment by category, Section 7.3 | Exercise report |
| RC.RP Recovery plan execution (A.5.29, A.5.30) | Business Continuity Response Plan, Section 8 | Disaster recovery test report |
| RC.CO Recovery communication (A.5.29) | Communication during recovery, Section 8.2 | Disaster recovery test report |

# Risk Assessment

## Method

Risk is managed to ISO/IEC 27005:2022.

- Identification. Asset-based, for the signing key, citizen data, card stock, production integrity, the audit trail and availability; and event-based, for what an attacker would set out to achieve, such as a card produced for a person not entitled to one.

- Analysis. Likelihood and impact rated on the scales in Section 4.2, before and after treatment.

- Treatment. Each risk modified, avoided, shared or retained, with its controls in Section 5.2, recorded in the template in Section 5.3.

- Acceptance. Residual risk accepted by the authority set in Section 4.2.

- Monitoring and review. By the Security Working Group, at each gate in weeks 6, 17, 26 and 30, at handover, and quarterly in operation.

The register in Section 4.3 is the baseline adopted at mobilization, and it is refined by threat modeling during design.

## Risk criteria and assessment matrix

| Likelihood | Impact |
| --- | --- |
| 1 Rare: not expected over the life of the System | 1 Negligible: no data exposed, no production effect |
| 2 Unlikely: needs a combination of failures or a capable attacker | 2 Minor: error caught before dispatch; up to one shift lost |
| 3 Possible: has occurred in comparable systems | 3 Moderate: limited data exposure or incorrect cards recalled; up to one day lost |
| 4 Likely: expected to be attempted during the life of the System | 4 Major: data of many citizens exposed, blank stock lost, or several days lost |
| 5 Almost certain: expected to occur repeatedly | 5 Severe: a genuine card for a person not entitled to it, compromise of the signing key, or bulk exfiltration of biometric data |

The rating is likelihood multiplied by impact.

| Impact \ Likelihood | 1 Rare | 2 Unlikely | 3 Possible | 4 Likely | 5 Almost certain |
| --- | --- | --- | --- | --- | --- |
| 5 Severe | 5 Medium | 10 High | 15 High | 20 Critical | 25 Critical |
| 4 Major | 4 Low | 8 Medium | 12 High | 16 High | 20 Critical |
| 3 Moderate | 3 Low | 6 Medium | 9 Medium | 12 High | 15 High |
| 2 Minor | 2 Low | 4 Low | 6 Medium | 8 Medium | 10 High |
| 1 Negligible | 1 Low | 2 Low | 3 Low | 4 Low | 5 Medium |

| Band and rating | Treatment | Residual risk accepted by |
| --- | --- | --- |
| Critical, 20 to 25 | The activity does not proceed until the risk is reduced | Not accepted |
| High, 10 to 16 | Treated before the gate at which it is reviewed | Purchaser's Project Manager, time-bound with a treatment plan |
| Medium, 5 to 9 | Treated where cost-effective, then monitored | NRB security officer |
| Low, 1 to 4 | Monitored through routine controls | Risk owner |

## Risk identification register

Ratings are likelihood × impact. Each risk is owned by the Supplier during implementation and by the NRB role shown from handover. Its controls are set out in Section 5.2.

| Risk | Inherent | Residual | Owner from handover |
| --- | --- | --- | --- |
| C01 The Document Signer key is used outside an authorized production job, or extracted | 3 × 5 = 15, High | 1 × 5 = 5, Medium | NRB security officer |
| C02 A card is produced for a person not entitled to it, by an insider acting alone or in collusion | 3 × 5 = 15, High | 1 × 5 = 5, Medium | NRB operations manager |
| C03 Blank, rejected or personalized cards are stolen or diverted | 3 × 4 = 12, High | 1 × 4 = 4, Low | NRB operations manager |
| C04 Citizen demographic or biometric data is exfiltrated | 3 × 5 = 15, High | 2 × 4 = 8, Medium | NRB security officer |
| C05 Ransomware encrypts or destroys the production estate | 4 × 5 = 20, Critical | 2 × 3 = 6, Medium | NRB ICT manager |
| C06 Administrator credentials are stolen through phishing or reuse | 4 × 5 = 20, Critical | 2 × 4 = 8, Medium | NRB security officer |
| C07 Forged requests or altered data on the NRIS interface | 2 × 5 = 10, High | 1 × 5 = 5, Medium | NRB security officer |
| C08 The personalization or mailing control systems are compromised, or left vulnerable by the manufacturer's patch schedule | 3 × 4 = 12, High | 2 × 3 = 6, Medium | NRB ICT manager |
| C09 Tampered or counterfeit hardware or software is delivered | 2 × 5 = 10, High | 1 × 4 = 4, Low | NRB ICT manager |
| C10 A vulnerability in software written under the Contract is exploited | 3 × 4 = 12, High | 2 × 3 = 6, Medium | NRB ICT manager |
| C11 Audit records are altered to conceal unauthorized activity | 3 × 4 = 12, High | 1 × 4 = 4, Low | NRB security officer |
| C12 Remote support is abused, or citizen data leaves Malawi through support or factory work | 3 × 4 = 12, High | 1 × 4 = 4, Low | NRB security officer |
| C13 The primary site or its storage is lost | 2 × 5 = 10, High | 2 × 3 = 6, Medium | NRB ICT manager |
| C14 The Document Signer certificate lapses, or its algorithm weakens within the ten year card life | 3 × 4 = 12, High | 1 × 4 = 4, Low | NRB security officer |
| C15 Security alerts are missed, or NRB cannot operate the controls after handover | 3 × 4 = 12, High | 2 × 3 = 6, Medium | NRB security officer |

## Risk position before and after treatment

Inherent.

| Impact \ Likelihood | 1 Rare | 2 Unlikely | 3 Possible | 4 Likely | 5 Almost certain |
| --- | --- | --- | --- | --- | --- |
| 5 Severe |  | C07, C09, C13 | C01, C02, C04 | C05, C06 |  |
| 4 Major |  |  | C03, C08, C10, C11, C12, C14, C15 |  |  |
| 3 Moderate |  |  |  |  |  |

Residual.

| Impact \ Likelihood | 1 Rare | 2 Unlikely | 3 Possible | 4 Likely | 5 Almost certain |
| --- | --- | --- | --- | --- | --- |
| 5 Severe | C01, C02, C07 |  |  |  |  |
| 4 Major | C03, C09, C11, C12, C14 | C04, C06 |  |  |  |
| 3 Moderate |  | C05, C08, C10, C13, C15 |  |  |  |

Treatment moves all 15 risks out of the High and Critical bands: 2 Critical and 13 High before treatment become 10 Medium and 5 Low after it. The three risks that remain at impact 5, C01, C02 and C07, cannot be made less severe, only less likely and quicker to detect. Each has a dedicated detection rule and is reviewed at every Security Working Group.

# Mitigation and Control Strategy

## Control strategy

| Rule | Application |
| --- | --- |
| Remove the risk before controlling it | No citizen data at the factory or in development, no internet-facing service at go-live, no copy of the signing key outside the modules, no standing remote access |
| Three layers for every severe risk | Each risk of impact 5 has a preventive control, a detective control that makes it visible within the shift, and a corrective control that limits the outcome |
| Engineered before administrative | A control the System enforces, such as a release that requires a second role, is preferred to one that relies on a procedure being followed |
| Every control verified | A control counts toward residual risk only once a test has shown it works, under Section 6.2 |

Against an insider with legitimate access, prevention can only go so far, because the access needed to commit the act is the access needed to do the job. Each insider risk is therefore paired with a reconciliation or behavior rule that finds the act within the shift.

## Controls by risk

| Risk | Principal controls |
| --- | --- |
| C01 Signing key misused or extracted | Key generated inside FIPS 140 validated modules and not exportable; Signing Service the sole client of the modules, signing only for released jobs; module administration under a quorum of custodians; signatures reconciled against requests and blanks issued |
| C02 Card produced for a person not entitled | Production only from records released in NRIS; operator runs and supervisor releases; serialized reconciliation every shift; untraceable cards rejected at quality control; behavior analytics |
| C03 Cards stolen or diverted | Serialized stock; secure store under biometric access; destruction under dual custody with certificate; card-to-carrier matching |
| C04 Citizen data exfiltrated | Biometric data held only for the batch in production; AES-256 at rest; Database Zone behind the firewall; removable storage disabled; outbound traffic restricted; retrieval volumes monitored |
| C05 Ransomware | Endpoint detection and response; segmentation; hardened baselines; immutable backups under separate credentials; tested recovery |
| C06 Administrator credentials stolen | Multi-factor authentication; privileged access issued per session and recorded; administration only through the administrative access host; awareness training |
| C07 NRIS interface abused | Mutual certificate authentication; integrity check and validation of every exchange; requests accepted only if released in NRIS |
| C08 Equipment control systems compromised | Machine Control Zone on its own VLAN, reached only through the firewall pair; removable media controlled; integrity baseline from factory acceptance; compensating firewall rules within seven days of an advisory |
| C09 Tampered hardware or software | Supply through authorized channels; inspection on delivery; secure boot and signed firmware; software hashes verified |
| C10 Application vulnerability | Secure development lifecycle; static and dynamic testing; release gate; independent penetration testing |
| C11 Audit records altered | Write-once audit storage; events forwarded to monitoring and to NRB's Security Operations Center; auditor role separate from administrator |
| C12 Remote support abused or data leaves Malawi | No standing remote access; each session approved by NRB and recorded; synthetic data at the factory; personal data removed from logs |
| C13 Primary site lost | Secondary environment replicating within five minutes; immutable offsite backups; annual disaster recovery test |
| C14 Certificate lapses or algorithm weakens | Expiry alerts at 180, 90 and 30 days; renewal lead time agreed with e-Government; certificate reference recorded on every card |
| C15 Alerts missed or NRB not ready | Detection rules derived from this register; S1 and S2 alerts by SMS; three security engineers trained for two posts; Security Operations Center run by NRB under observation before transfer |

## Mitigation and control strategy template

Each risk is treated through a record in this form, created when the risk is identified and closed only when the residual risk has been verified and accepted.

| Field | Content |
| --- | --- |
| Risk ID, title and owner | Register identifier; the role accountable during implementation and from handover |
| Risk scenario | Asset, threat source, what happens, and the consequence |
| Inherent rating | Likelihood, impact and band, on the scales of Section 4.2 |
| Treatment option | Modify, avoid, share or retain |
| Preventive controls | Each control, with its ISO/IEC 27001 Annex A reference and System Architecture reference |
| Detective controls | Each control, with its detection rule in security monitoring |
| Corrective controls | The incident category in Section 7.3 and the recovery scenario in Section 8.1 |
| Actions | Each implementation action, who performs it and the week it is due |
| Verification | The test or evidence that shows each control works, and its acceptance criterion |
| Residual rating | Likelihood, impact and band after verified treatment |
| Acceptance | Accepting authority, name and date |
| Review | Next review date and the events that trigger an earlier one |

# Implementation Method Statement

## Security activities by phase

Security runs through every phase of the Implementation Sub-Plan in Preliminary Project Plan Section 2.1, and the milestones below carry a security condition.

| Phase and weeks | Security activities | Security condition |
| --- | --- | --- |
| Mobilization and planning, weeks 1 to 2 | Security Working Group formed; personnel screened and inducted; risk register baselined; escalation matrix issued |  |
| Design and detailed planning, weeks 3 to 6 | Threat modeling of the design; Privacy Impact Assessment; Security Design Documentation, including the access control matrix, key management procedures and hardening guide; policies drafted; certificate profile agreed with e-Government | Detailed Design Approval: no High risk without an approved treatment |
| Procurement and manufacturing, weeks 7 to 16 | Secure development with static and dynamic testing; equipment control PCs hardened with the manufacturer; ICT ordered through authorized channels; synthetic data only |  |
| Factory acceptance testing, week 17 | Equipment hardening verified; integrity baseline of the control software recorded | Successful FAT: baseline recorded |
| Installation and site acceptance testing, weeks 21 to 26, with the ICT from week 15 | Equipment inspected on delivery; firewalls, directory, multi-factor authentication, privileged access management and monitoring built before the hosts they protect; key ceremony witnessed by NRB in week 16; secondary environment to the same baselines; security testing and penetration testing; integration with NRB's Security Operations Center | Installation and SAT: no Critical or High finding open; no citizen data before this point |
| Training and knowledge transfer, weeks 25 to 28 | Security training; incident response exercise | Training completed |
| Commissioning, weeks 27 to 30 | Operational acceptance tests 9 to 12; NRB runs the Security Operations Center under observation | System commissioned |
| Handover and go-live, weeks 31 to 32 | Security Operations Center transferred; credentials rotated; residual risks accepted by NRB | Full handover |

## Security testing

| Test and weeks | Exit criterion |
| --- | --- |
| Static and dynamic testing of software written under the Contract, weeks 7 to 16 | No unresolved high severity finding in a promoted release |
| Pre-commissioning test 5, cybersecurity and access control, week 19 | Security Readiness Report |
| Pre-commissioning test 13, backup and recovery, including failover, week 20 | Backup and Recovery Test Report |
| Security testing, weeks 20 and 21: vulnerability assessment, authentication, encryption validation, configuration against the hardened baselines, and simulation of the activity each detection rule for a High or Critical risk must catch | Findings rated and entered for remediation; each tested rule raised its alert |
| Independent penetration testing of the full deployed configuration, including the Machine Control Zone, week 24 | Report delivered unedited to the Purchaser |
| Remediation and retest, weeks 25 and 26 | No Critical or High finding open |
| Operational acceptance tests 9 to 12, week 27 | Success criteria of Table B |

The penetration tester is independent of the Supplier, and its scope and rules of engagement are approved by NRB before testing begins.

## Handover and operation

At handover. Every privileged credential known to the Supplier is rotated, break-glass credentials are re-sealed for NRB custodians, the module administrator credentials are re-issued to the custodians NRB designates, and Supplier access is reduced to named support accounts usable only with NRB's approval. As-built security documentation, the policies and procedures, and the risk register with each residual risk accepted are handed over with the Security Operations Center.

In operation. NRB operates the Security Operations Center, and the Supplier provides the following within its warranty and support obligations:

- Monthly. Patch cycle; vulnerability scan; Security Working Group; cyber security compliance status report.

- Quarterly. Vulnerability assessment report; privileged access recertification; risk register review.

- Annually. Independent penetration test; disaster recovery test; incident response exercise; policy review.

Critical vulnerabilities are mitigated within 72 hours and remediated within 14 days, and High within 30 days. On the equipment control systems, where releases follow the manufacturer's schedule, a compensating control is applied within 7 days of a Critical advisory.

Compliance reporting. The report required by SCC 19.6(d), on the status of compliance with cyber security risk management and on foreseeable risks and their mitigation, is issued monthly from week 4. It covers control implementation, open vulnerabilities by severity and age, patching, incidents and notifications, changes to the risk register, and certificates nearing expiry.

# Incident Response Plan

## Team and escalation matrix

The plan is aligned with NIST Special Publication 800-61 Revision 3 and uses the incident classes S1 to S4 defined in System Architecture Section 10.7.

| Role | During implementation | From handover |
| --- | --- | --- |
| Incident manager | Supplier security lead | NRB security officer |
| Technical lead | Supplier security lead | Supplier security lead, at Level 2 and above |
| Security Operations Center analysts | Supplier on-call security engineer | NRB security engineers |
| Notified and informed | Purchaser's Project Manager and NRB security officer | Purchaser's Project Manager |
| Consulted | NRB data protection officer; e-Government for certificates; the equipment manufacturer for the production lines | The same |

| Class and acknowledgement | Escalated to | Purchaser notified |
| --- | --- | --- |
| S1, critical: acknowledged within 15 minutes | Immediately to the incident manager, technical lead, NRB security officer and the Purchaser's Project Manager | Immediately, and in writing within 24 hours |
| S2, major: acknowledged within 15 minutes | Immediately to the incident manager, technical lead and NRB security officer | Immediately, and in writing within 24 hours |
| S3, moderate: acknowledged within 1 hour | Incident manager and technical lead | In writing within 24 hours |
| S4, minor: acknowledged next business day | Recorded | In the monthly report |

Names, telephone numbers and email addresses are added at mobilization, verified quarterly and re-issued at handover. S1 and S2 alerts reach on-call staff by SMS as well as on the console.

## Response process

| Stage | What is done |
| --- | --- |
| Detect and classify | Alert triaged and classified S1 to S4 |
| Notify | Incident declared and escalated by the matrix; the Purchaser notified |
| Contain | Affected component isolated, accounts disabled, signing or production suspended where required |
| Preserve | Logs, memory and disk images captured before anything is rebuilt, under System Architecture Section 10.7 |
| Investigate | Scope and root cause established, and the cards and citizens affected identified from the audit trail |
| Eradicate and recover | Hosts rebuilt from the hardened baselines, credentials rotated, service restored under Section 8. After an S1 incident, production resumes only on NRB's written decision |
| Close | Final report and lessons learned entered in the risk register |

## Contractual incident categories

Each category listed in SCC 19.7 has a playbook. Their first actions are:

| SCC 19.7 category | Class | First actions |
| --- | --- | --- |
| (a) Personal data breach | S1 if exfiltration is confirmed, otherwise S2 | Block the outbound path; disable the accounts involved; isolate the host; identify the records affected |
| (b) Biometric data breach | S1 | As for (a); identify the batches present at the time, which bounds the citizens affected |
| (c) Cryptographic key compromise | S1 | Suspend signing; withdraw the Signing Service's module credentials; ask e-Government to revoke the certificate; list the cards signed in the affected period |
| (d) Unauthorized card production or issuance | S1 | Stop the job; quarantine the cards; secure the camera record; suspend the accounts involved |
| (e) Ransomware and malware | S1, or S2 for a single contained host | Isolate the segment; disable compromised accounts; preserve evidence; recover from immutable backups |
| (f) Unauthorized privileged access | S2, or S1 if it reaches signing or the production lines | Terminate sessions; disable the account; rotate the credentials it could reach |
| (g) Compromise of personalization systems | S2, or S1 if cards were produced improperly | Stop the affected line while the other continues; verify against the integrity baseline |
| (h) Compromise of mailing systems | S2 | Stop the affected line; hold and re-check its mail pieces |
| (i) Fraudulent card production or issuance attempts | S2, or S1 if a card was produced | Preserve the records; restrict the accounts involved; report to NRB |
| (j) Incident likely to affect NRIS | S1 or S2 by effect | Suspend the exchange with NRIS; revoke the interface certificate if compromise is suspected; notify NRB |

## Notification and reporting

| Report | When | Content |
| --- | --- | --- |
| Initial notification | Immediately on detection | What has been seen, its class, and the first actions |
| Written report | Within 24 hours | What happened; systems, data and cards potentially affected; containment so far; next update |
| Final report | Within 10 business days of containment | Timeline, root cause, cards and citizens affected, actions, lessons learned |

NRB, as data controller, decides on and makes any notification required by the Data Protection Act 2024 and any report to law enforcement, supported by the Supplier's reports. The Supplier makes no public statement. The plan is exercised in week 28 and annually, and reviewed after every S1 or S2 incident.

# Business Continuity Response Plan

## Recovery targets and scenarios

NRIS is the system of record, so a disruption delays cards and does not lose them, provided the record of every card produced and in progress, and the means of signing cards, are preserved. The recovery targets are those of System Architecture Section 9.3: automatic failover within 60 seconds, full service recovery within 5 to 15 minutes, data loss of not more than 5 minutes, and availability of not less than 99 percent. They are confirmed with the Purchaser during design.

| Scenario | Response and decision |
| --- | --- |
| Loss of a host, switch, firewall, load balancer or storage controller | Automatic failover within the facility; the component repaired under the support model |
| Loss of the hardware security module at the primary site | Signing continues on the module at the secondary site, over the encrypted connection between the sites; the module replaced under the support model |
| Loss of a personalization or mailing line | Production continues on the other line |
| Loss of the primary storage array or site | The secondary environment carries the data and application services and keeps every record available to NRIS; production resumes when the primary platform and equipment are available. Invoked by NRB's business continuity manager |
| Ransomware or a destructive attack | Incident Response Plan first. Hosts rebuilt from the hardened baselines; data restored from the most recent immutable copy verified as clean, on an isolated segment; credentials replaced. The secondary environment is checked before it is trusted, because replication may have carried the damage. Directed by the incident manager, with NRB |
| Loss of both hardware security modules, or compromise of the signing key | New key pair generated at a ceremony and a new certificate requested from e-Government. Decided by NRB |
| Government Wide Area Network or NRIS unavailable | Production continues on records already retrieved; status events held and sent on restoration, under System Architecture Section 7.15 |

Restoration follows a fixed order, so that each service depends only on what is already running: network and directory, security monitoring, database, integration gateway, application services, Signing Service, then the production lines.

## Activation, communication and testing

Failover within the facility is automatic. Invocation of the secondary environment and the response to a site loss are decided by NRB's business continuity manager on the advice of the Supplier's technical lead. NRB communicates with registration offices and the public; the Supplier keeps NRB management, the NRIS team and, for a security incident, the Purchaser's Project Manager informed.

Security is not relaxed during recovery. The secondary environment has its own firewall, encryption and monitoring, break-glass access raises an alert and is rotated after use, emergency changes are reviewed afterwards, and restored data is verified before service resumes.

Recovery is tested, not only written:

- Week 20. Pre-commissioning test 13: backup, restoration and failover to the secondary environment.

- Week 27. Operational acceptance test 11: backup and restoration in live operation.

- Annually. Disaster recovery test, simulating full system failure, with the recovery point and time achieved recorded.

The business continuity and disaster recovery procedures are delivered in week 19, and corrected after every test.

# Resources, Schedule and Capacity Building

## Cybersecurity work breakdown structure

| Work package | Main deliverables | Weeks and lead |
| --- | --- | --- |
| 1. Governance and management | Security Working Group; policies; monthly compliance reports | Weeks 1 to 32; Cybersecurity and PKI Specialist |
| 2. Risk management | Risk register; threat model; Privacy Impact Assessment; risk acceptance at handover | Weeks 1 to 32; Cybersecurity and PKI Specialist |
| 3. Security design | Security Design Documentation; hardening guide; detection rules | Weeks 3 to 17; Solution Architect |
| 4. Secure build and supply chain | Release gate records; equipment hardening and integrity baseline; delivery inspection | Weeks 3 to 21; Software Integration Specialist |
| 5. Security implementation | Hardened platform and security stack; key ceremony; secondary environment; Machine Control Zone; integration with NRB's Security Operations Center | Weeks 15 to 25; Network Engineer and CPF Infrastructure Engineer |
| 6. Security testing | Pre-commissioning tests 5 and 13; security test report; penetration test and retest; operational acceptance tests 9 to 12 | Weeks 19 to 27; Quality Assurance and Testing Specialist |
| 7. Incident response and continuity | Incident Response Plan; Business Continuity Response Plan; exercise report | Weeks 2 to 28; Cybersecurity and PKI Specialist |
| 8. Capacity building | Shadowing; security training; Security Operations Center run by NRB under observation | Weeks 15 to 30; Training and Change Management Specialist |
| 9. Handover | Transfer of the Security Operations Center; credential rotation; as-built security documentation | Weeks 31 to 32; Cybersecurity and PKI Specialist |

## Timeline

Figure 9.1: Cybersecurity timeline by work package, against the ten contractual milestones of the Information System schedule in Preliminary Project Plan Section 2.2. Solid bars are the Supplier's work; hatched bars are performed with or by NRB; open diamonds are security gates and events.

## Resource and skill matrix

| Role | Leads | Contributes to |
| --- | --- | --- |
| Cybersecurity and PKI Specialist | Governance and risk; PKI and key management; monitoring and incident response; security testing; knowledge transfer | Network security; application security; equipment control systems |
| Solution Architect | Security architecture and design | Risk assessment; PKI; application security; testing |
| Network Engineer | Network zones, firewalls and intrusion prevention | Monitoring; Machine Control Zone; testing |
| CPF Infrastructure Engineer | Hardened platform, secondary environment, backup and recovery | Monitoring; key management infrastructure; testing |
| Software Integration Specialist | Secure development and interface security | PKI for interface certificates; testing |
| Secure Personalization System Engineer | Equipment control systems, with the manufacturer | Knowledge transfer |
| Quality Assurance and Testing Specialist | Security test programme and traceability | Risk assessment |
| Training and Change Management Specialist | Security training delivery |  |
| Supplier security engineers | Security monitoring and on-call response until handover | Testing; knowledge transfer |
| Independent penetration tester | Penetration testing |  |

| Role | Qualifications | Engagement |
| --- | --- | --- |
| Cybersecurity and PKI Specialist, proposed for the Cyber Security Expert position | Degree in cybersecurity, computer science or information security; experience with hardware security modules, encryption and certificates | Weeks 1 to 32, on site from week 15; then Level 2 security support through the warranty period |
| Network Engineer | CCNA and CCNP; at least five years on firewalls and secure government networks | Design; weeks 15 to 23 |
| Supplier security engineers | Experience in security monitoring and incident response | Weeks 16 to 32 |
| Independent penetration tester | Independent of the Supplier; CREST accredited or equivalent | Week 24, retest in weeks 25 and 26, then annually |

The qualifications of the other roles are set out in the Key Personnel CVs.

## Capacity building and knowledge transfer

The aim is that NRB operates the facility's security without the Supplier at handover, and has already done so under observation. Three security engineers are trained for two posts, under the Training Sub-Plan in Preliminary Project Plan Section 3.

| Activity | Participants |
| --- | --- |
| Shadowing of the security build, the key ceremony and the security tests, weeks 15 to 26 | NRB security engineers and administrators |
| Security administration module, two days, weeks 26 and 27 | Security engineers, system administrators |
| Security and compliance module, weeks 25 and 26 | All users, and managers |
| Incident response exercise, week 28 | Security engineers, administrators, NRB security officer |
| Security Operations Center run by NRB under observation, weeks 27 to 30 | Security engineers |

Transfer criteria. The Security Operations Center is transferred once each NRB security engineer has shown, under observation, that they can classify and escalate alerts, apply the playbooks of Section 7.3 to containment, run an access recertification, operate the hardware security modules under dual control, restore a server from the immutable backups, and produce the monthly compliance report.

# Innovations

| Innovation | What it does |
| --- | --- |
| Closed-loop production integrity, answering C01, C02 | Security monitoring reconciles NRIS requests, signatures made by the hardware security modules and serialized blanks issued, for every job and every shift, and raises an S1 alert on any difference. A card produced for the wrong person, which no single control would notice, is found in the shift in which it is made |
| Detection derived from the risk register, answering all risks | Every High or Critical risk is linked to a detection rule, a playbook and a test showing the rule fires, so that the Security Operations Center watches for the outcomes this facility fears rather than for generic attacks alone |
| Cyber-physical correlation, answering C02, C03, C06 | Access control and intrusion events are correlated with system events, so that a privileged session opened from a room no authorized person has entered, or the card store opened outside a shift, raises an alert |
| Bounded exposure by design, answering C04 | Biometric data is held only for the batch in production, and the audit trail records which batches were present at any moment, so a breach can be scoped to the citizens actually exposed |
| Integrity baseline from the factory, answering C08, C09 | The hashes of the equipment control software accepted at factory acceptance are the reference against which the installed lines are verified on arrival, after each release and on any alert |
| Targeted reissue, answering C01, C14 | Each card records the certificate under which it was signed, so that if a key were compromised or an algorithm weakened, only the affected cards need be identified and reissued |

# Compliance

## Compliance and governance statement

The Proposer confirms that, if awarded the Contract, it will:

- design, implement and maintain the security architecture required by Section VII clause 1.6, as described in System Architecture Section 10 and governed by this plan;

- take the technical and organizational measures required by GCC 44.1, and flow those obligations down to its subcontractors, suppliers and manufacturers;

- notify the Purchaser's Project Manager and designated security representatives immediately, and in any event within 24 hours, of the cyber security incidents listed in SCC 19.7, as set out in Section 7.4;

- report monthly on the status of compliance with cyber security risk management, and on foreseeable cyber security risks and their mitigation, as required by SCC 19.6(d);

- store and process citizen data only in Malawi, with NRB as data controller, and use synthetic or masked data for all work outside the production system;

- comply with the Data Protection Act 2024, the Communications Act 2016, the National Registration Act 2015, the Electronic Transactions and Cybersecurity Act 2016, Malawi's National Digitalization Policy, the Project Environmental and Social Management Plan, the principles of the General Data Protection Regulation, and data minimization and purpose limitation;

- ensure that Inkript, the joint venture member responsible for the Information System, maintains its ISO/IEC 27001 certification throughout the Contract; and

- assign security decisions as set out in Section 2.1, with residual risk accepted only by the Purchaser.

## Requirements compliance matrix

| Requirement | Response |
| --- | --- |
| Section VII clause 1.6.1, Security architecture. Multi-layered security architecture | Complies. System Architecture Section 10.1; Section 3.1 |
| Section VII clause 1.6.2, Security architecture requirements. Encryption in transit and at rest, zero trust, RBAC and least privilege, segmented network, secure APIs, HSMs, key lifecycle, MFA for privileged access, tamper-proof audit trails | Complies. System Architecture Sections 9.2, 10.1 to 10.6 |
| Section VII clause 1.6.3, Data protection. AES-256 at rest, TLS 1.2 or higher, masking, secure deletion, retention enforcement | Complies. System Architecture Section 10.2 |
| Section VII clause 1.6.4, Identity and access management. Centralized IAM, MFA, PAM, just-in-time access, access logging, recertification | Complies. System Architecture Section 10.3 |
| Section VII clause 1.6.5, Application security. Secure development lifecycle, OWASP Top 10, SAST and DAST, API security, vulnerability and patch management | Complies. System Architecture Section 10.5; Section 6.2 |
| Section VII clause 1.6.6, Infrastructure security. CIS-hardened systems, EDR, anti-malware and IPS, next generation firewalls, secure baselines, SIEM | Complies. System Architecture Sections 9.1, 9.2 and 10.7 |
| Section VII clause 1.6.7, Physical security. Biometric access, CCTV, secure zones, environmental monitoring linked to alerts, visitor logging | Complies. Installed under the facility works and integrated with security monitoring. System Architecture Section 9.5 |
| Section VII clause 1.6.8, Security monitoring and incident response. SOC, 24/7 monitoring, SIEM, incident response plan, escalation matrix, forensics, reporting timelines | Complies. System Architecture Section 10.7; Section 7 |
| Section VII clause 1.6.9, Vulnerability and penetration testing. Independent penetration test before go-live and annually; quarterly vulnerability assessment; remediation tracking | Complies. Sections 6.2 and 6.3 |
| Section VII clause 1.6.10, Business continuity and disaster recovery. Encrypted, offsite and immutable backups; failover; annual DR test; ransomware recovery | Complies. System Architecture Sections 9.3 and 12.3; Section 8 |
| Section VII clause 1.6.11.1, Accreditation. Compliance of the bidder and key personnel with recognized standards | Complies. Section 9.3 |
| Section VII clause 1.6.11.2, Certification. ISO/IEC 27001, mandatory; ISO 9001 and ISO/IEC 20000-1, preferred | ISO/IEC 27001 and ISO 9001: complies, certificates attached |
| Section VII clause 1.6.11.3, Frameworks. NIST CSF, CIS Controls, ISO/IEC 27002, OWASP | Complies. Section 3.2; System Architecture Section 10.8 |
| Section VII clause 1.6.11.4, Cryptography. FIPS 140-2 or 140-3 HSMs, X.509, eIDAS-aligned signatures | Complies. System Architecture Section 10.4 |
| Section VII clause 1.6.11.5, Legal and regulatory. Malawi legislation, ESMP, GDPR principles, minimization, Privacy Impact Assessment | Complies. Section 11.1; System Architecture Section 10.2 |
| GCC 44.1. Cyber security measures, including by subcontractors | Complies. Sections 2.1 and 11.1 |
| SCC 19.6(d). Report on compliance with cyber security risk management | Complies. Section 6.3 |
| SCC 19.7. Notification within 24 hours of listed incidents | Complies. Section 7 |