Preliminary Project Plan - Information System Sub-Plans

Table of Contents

1. Scope and Approach	3

1.1 Scope of the sub-plans	3

1.2 Delivery approach	3

2. Implementation Sub-Plan	5

2.1 Methodology and phases	5

2.2 Schedule	6

2.3 Discovery and information gathering	9

2.4 Design and process re-engineering	10

2.5 Build, installation and integration	11

2.6 Transition to production	13

2.7 Dependencies on the Purchaser and other parties	13

2.8 Responsibility assignment	15

2.9 Implementation risks and mitigation	16

2.10 Documentation deliverables	18

3. Training Sub-Plan	21

3.1 Approach and knowledge transfer	21

3.2 Recommended trainees and prerequisites	22

3.3 User training	23

3.4 Technical training	24

3.5 Management training	25

3.6 Schedule, location and training environment	26

3.7 Assessment, certification and operational independence	27

3.8 Supplier trainers and sample materials	28

4. Testing and Quality Assurance Sub-Plan	31

4.1 Test strategy and levels	31

4.2 Test environments and test data	32

4.3 Factory acceptance testing	33

4.4 Integration and security testing	34

4.5 Pre-commissioning tests	35

4.6 Operational acceptance tests	36

4.7 Defect management and quality assurance	38

5. Warranty Defect Repair and Technical Support Service Sub-Plan	40

5.1 Coverage and periods	40

5.2 Support organization and service desk	41

5.3 Service levels and performance indicators	41

5.4 Preventive and corrective maintenance	42

5.5 Spare parts and consumables	43

5.6 Service reporting, review and handover	44

Annex A. Licensing Bill of Materials	45

# Scope and Approach

## Scope of the sub-plans

The Implementation, Training, Testing and Quality Assurance, and Warranty Defect Repair and Technical Support Service sub-plans cover the Information System: the two laser personalization systems, the two mailing and dispatch systems, the application software, the integration with NRIS, the supporting ICT infrastructure at the Card Production Facility and in the secondary environment, the security components, and the supply of polycarbonate cards as it bears on production. The system itself is described in the System Architecture.

| Sub-plan | Section |
| --- | --- |
| Implementation Sub-Plan | Section 2 |
| Training Sub-Plan | Section 3 |
| Testing and Quality Assurance Sub-Plan | Section 4 |
| Warranty Defect Repair and Technical Support Service Sub-Plan | Section 5 |
| Licensing Bill of Materials | Annex A |

Boundary with the facility works. The civil and architectural works, electrical installation, HVAC and environmental control, fire detection and suppression, and the physical security installations are planned under the facility works. They appear here only where the Information System depends on them, chiefly the readiness of the server room and production floor for installation, and that dependency is scheduled in Section 2.

Boundary with project organization. Project management authorities, the project-wide schedule and the staffing of the project team are set out in the Project Organization and Management Sub-Plan. The schedule in Section 2 is the Information System's part of it and uses the same ten contractual milestones.

## Delivery approach

The contractual Implementation Schedule sets ten milestones over 32 weeks from the Effective Date. The Information System is delivered against those milestones in parallel workstreams, joined at defined points, under the following principles:

| Principle | Effect on the plan |
| --- | --- |
| Design approved before build | Nothing the design can change is built or configured before design approval. Three things it cannot change start earlier: the equipment, ordered at mobilization and built on its standard configuration, with its options fitted after approval; the ICT infrastructure, ordered at mobilization in the quantities already fixed, and configured to the approved design; and the application components the Technical Requirements fully define, built from week 3 |
| Integration risk retired early | The NRIS interface is specified during design, built and tested against simulators from week 7, and tested against the NRIS test environment on site. The first contact with NRIS is not the first test of the interface |
| Nothing reaches the production line untested | Each component passes factory acceptance, staging integration, pre-commissioning and operational acceptance in turn, and a failure at one stage is corrected before the next begins |
| Citizen data stays in Malawi | Every activity performed away from Malawi, including build, staging and factory acceptance testing, uses synthetic data. Citizen data is used only on the installed system |
| Knowledge transfer alongside delivery | NRB technical staff attend factory acceptance testing, shadow installation and commissioning, and are trained on the system as deployed. Operational independence is built during delivery rather than attempted at the end |
| The Purchaser's inputs are dated | Every input the plan depends on is stated with the week it is needed, in Section 2.7, so that a late input is visible as a schedule risk before it becomes a delay |

The principle that shapes the schedule most is the second. The interface to NRIS is built by two teams in two organizations, and on the Purchaser's side it is still to be developed. An interface tested for the first time on site in week 23 would leave three weeks to find and correct every disagreement between two independently written halves. Specifying it in week 6, testing the production side against simulators from week 7, and integrating each interface with NRIS as it is delivered from week 18 moves that discovery forward by months.

# Implementation Sub-Plan

## Methodology and phases

Implementation follows the ten contractual milestones as phases. Each phase ends at a defined output, and a phase that feeds the next is not closed until its output has been accepted.

| # | Phase | Weeks | Contractual milestone | Information System outputs |
| --- | --- | --- | --- | --- |
| 1 | Mobilization and planning | 1 to 2 |  | Team mobilized, Purchaser inputs confirmed, schedule baselined, long-lead equipment and ICT infrastructure ordered |
| 2 | Design and detailed planning | 3 to 6 | Detailed Design Approval | High-Level and Low-Level Design, Interface Control Documents, future-state processes, card layout and card identifier, ICT site preparation requirements, network requirements for the Government Wide Area Network |
| 3 | Procurement and manufacturing | 7 to 16, with manufacture from week 3 |  | Equipment manufactured and fitted with the options fixed at design approval, ICT infrastructure delivered, application software built, production side of the NRIS interface built against simulators, blank cards manufactured |
| 4 | Facility renovation | 7 to 18 |  | Delivered under the facility works. Dependencies for the Information System: the server room handed over in week 14, and the production floor ready for installation in week 18 |
| 5 | Factory acceptance testing | 17 | Successful FAT | Equipment accepted at the factory on the actual card stock, Printer Control Service proven against the equipment software, NRB technical staff trained at the factory |
| 6 | Shipping and customs clearance | 18 to 20 | Equipment delivered on site | Equipment and the first card delivery on site |
| 7 | Installation and site acceptance testing | 21 to 26, with the ICT installation from week 15 | Installation and SAT complete | System installed and integrated, secondary environment operational, Document Signer key established, pre-commissioning tests passed, pilot production run |
| 8 | Training and knowledge transfer | 25 to 28 | Training completed | User, technical and management training under Section 3 |
| 9 | System commissioning and performance testing | 27 to 30 | System commissioned | Operational acceptance tests passed under Section 4 |
| 10 | Handover, go-live and closure | 31 to 32 | Full handover and go-live | As-built documentation, prepared progressively from week 27, operation of the Security Operations Center transferred, stabilization support, Operational Acceptance |

Workstreams. Within the phases the work runs in six workstreams, each with a single lead:

| Workstream | Scope | Lead |
| --- | --- | --- |
| Personalization and mailing equipment | Manufacture, factory acceptance, installation and commissioning of two laser personalization systems and two mailing and dispatch systems | Equipment manufacturer, under the Supplier |
| Application software | Card Personalization Management System, Data Preparation Service, Signing Service, Printer Control Service, Quality Control Management, Mailing and Dispatch Management System, Stock Control, monitoring and administration | Supplier |
| NRIS integration | Interface specification, production-side development, integration testing | Supplier, with NRB developers building the NRIS side |
| ICT infrastructure | Virtualization hosts, storage array, network, firewalls, hardware security modules, backup, workstations, secondary environment | Supplier |
| Security | Security controls, establishment of the Document Signer key with e-Government, Security Operations Center | Supplier |
| Polycarbonate cards | Card body design with NRB, manufacture, qualification on the laser systems, phased delivery | Card manufacturer, under the Supplier |

Where the workstreams join. Four points bind them together, and each is a scheduled event rather than an assumption: design approval in week 6, where every workstream's design is reviewed as one; factory acceptance in week 17, where the equipment, the application's interface to it and the card stock meet for the first time; integration from week 18, where the application meets NRIS; and pilot production in week 26, where every workstream has to work at once.

## Schedule

The Implementation Schedule leaves the delivery date of each line for the Proposer to specify. The Information System's delivery against each line is as follows. Weeks are counted from the Effective Date, and week 1 is the first week after it.

| Line | Subsystem or item | Delivery | Installation | Acceptance | Liquidated damages milestone |
| --- | --- | --- | --- | --- | --- |
| 1 | Project mobilization and planning | Week 1 | Week 1 | Week 2 |  |
| 2 | Design and detailed planning | Design submitted for approval, week 5 | Week 3 | Week 6 | Detailed Design Approval |
| 3 | Procurement and manufacturing | Equipment ready for factory acceptance, week 12 | Week 7 | Week 16 |  |
| 4 | Facility renovation | Under the facility works | Week 7 | Week 18 |  |
| 5 | Factory acceptance testing | Week 17 | Week 17 | Week 17 | Successful FAT |
| 6 | Shipping and customs clearance | On site, week 20 | Week 18 | Week 20 | Equipment delivered on site |
| 7 | Installation and site acceptance testing | ICT estate installed, week 17. Equipment installed, week 23. Pre-commissioning complete, week 26 | Week 21 | Week 26 | Installation and SAT complete |
| 8 | Training and knowledge transfer | Week 28 | Week 25 | Week 28 | Training completed |
| 9 | System commissioning and performance testing | Week 30 | Week 27 | Week 30 | System commissioned |
| 10 | Handover, go-live and closure | Week 32 | Week 31 | Week 32 | Full handover and go-live |

Figure 2.1: Information System schedule, summary. Black bars carry no float; hatched bars are work by the Purchaser or other parties; black diamonds are the contractual milestones.

Two lines start ahead of their contractual week. Nothing in the Contract requires work to wait for the start of its line, and starting earlier is how the schedule gains float without moving a milestone. Equipment manufacture begins on order in week 3 rather than in week 7, because only the options depend on the approved design, and they are fitted after approval. The ICT installation begins in week 15, when the server room is handed over, rather than waiting for the equipment in week 21, because the servers and the personalization equipment are separate supplies in separate rooms.

The critical path. Three chains have no float, and each is fixed by a contractual date:

| Chain | Why it has no float |
| --- | --- |
| Design approval in week 6, NRB's side of the interface to week 22, completion of integration in weeks 23 and 24, then pre-commissioning, pilot production and operational acceptance | Integration cannot finish before NRB's side is ready, and everything after it runs to the Installation and SAT milestone in week 26 |
| Factory acceptance in week 17, shipping and customs to week 20, equipment installation in weeks 21 to 23, equipment pre-commissioning to week 26 | Factory acceptance is fixed in week 17 and installation and SAT in week 26, and the work between them fills the interval |
| Training in weeks 25 to 28, leading to operational independence in week 28 | The training window is fixed by the Contract, and operational independence must be shown before the final demonstration begins |

The first is the one that runs through work outside the Supplier's control, which is why the NRIS side is followed as closely as the Supplier's own work, with a joint checkpoint every two weeks and each interface integrated as soon as it is delivered. The float created by starting manufacture early sits before factory acceptance: it protects the week 17 date, but cannot shorten what follows it. Design in weeks 1 to 6 and the handover in weeks 31 and 32 also carry no float, since each fills the interval to its contractual milestone.

Float on the other chains. Every other chain can slip by the float shown without moving a milestone:

| Chain | Needed by | Float |
| --- | --- | --- |
| Equipment ready for factory acceptance | Week 17 | Four weeks, finishing in week 12 on the assumed ten week manufacturing time |
| Document Signer certificate issued by e-Government | Week 26, for pilot production | Six weeks, with the certificate signing request in week 16 |
| First card delivery on site | Week 26, for pilot production | Five weeks. The factory acceptance stock is made in a separate first run |
| All 2,000,000 cards on site | Week 27, before commissioning | One week |
| Server room handed over | Week 15, for the ICT installation | Five weeks. A later handover moves the ICT track, which carries the same float, and no milestone |
| Secondary environment at Blantyre | Week 26 | Five weeks |
| Production floor ready for installation | Week 21, for the equipment installation | Two weeks |

The operational acceptance window is tight by design. The operational acceptance tests fill weeks 27 to 30, and the final acceptance demonstration requires continuous production over an agreed observation period. The plan is built on an observation period of ten working days in weeks 29 and 30. A longer period would move the commissioning milestone, which is why the observation period is among the decisions requested at design approval in Section 2.7.

## Discovery and information gathering

Discovery runs from week 1 into the first half of design, and establishes the facts the design depends on before any of it is written.

| Area | What is established | Method |
| --- | --- | --- |
| NRIS data | Where each field the card requires is held, its type, length and permitted values, how it behaves when absent, and how the photograph and signature are stored | Data dictionary review with NRB, then profiling of the NRIS test data |
| NRIS interfaces | The existing middleware connection to the database, the application programming interface NRB plans, authentication, and the status values the document tracker expects | Walkthrough with NRB developers |
| Data quality | The proportion of records complete enough to produce a card, photographs meeting ICAO specifications, name lengths against the card layout, and characters used in Chichewa text | Profiling of the NRIS test data against the draft validation rules |
| Current production and dispatch | How requests are released today, how completed cards are batched and dispatched to ordering offices, and how the document tracker and SMS notification are updated | Walkthrough at NRB with the staff who perform each step |
| Security and PKI | The e-Government certificate profile, certificate signing request procedure and issuing time | Working sessions with e-Government and NRB |
| Network | Government Wide Area Network capacity and latency between the Card Production Facility, NRIS and the Blantyre disaster recovery data center | Working session with NRB and e-Government, followed by measurement |
| Site | Equipment and server room positions on the floor plan, and access routes for delivery | Joint review with the facility works |

Why profiling comes before design rather than after. Validation rules written against a data dictionary describe the data as it was specified. Profiling the test data describes it as it is. A name longer than the card layout allows, a photograph that fails ICAO checks, or a field left empty in a large share of records is a design decision, not a defect to be found in pilot production. The Discovery Report records every such finding and the decision taken on it.

Output. A Discovery Report in week 4, covering each area above, the decisions it requires, and the Purchaser inputs still outstanding against the dates in Section 2.7.

## Design and process re-engineering

Design deliverables. Design runs in weeks 3 to 6 and is submitted for approval in week 5.

| Deliverable | Content |
| --- | --- |
| High-Level Design | Architecture, components and their interfaces, deployment across the primary and secondary environments, and the security architecture |
| Low-Level Design | Host, storage, network and database configuration, virtual machine allocation, IP addressing, VLANs, firewall policy, and the hardened baselines |
| Interface Control Documents | Every NRIS exchange: transport, operations, message structures, field definitions, schemas, error conditions and status values, agreed with NRB developers |
| Security Design Documentation | Controls, access model, key management, the Document Signer key procedure and certificate profile agreed with e-Government, and logging |
| Card layout and card identifier | The card layout produced with NRB in the joint redesign, the positions of variable data, the QR zone and the card identifier used on the mailing line, and the blank card numbering scheme, format and range for the Purchaser's approval |
| ICT Site Preparation Guide | What the facility works must provide for the Information System: floor positions, loads, power per position, heat load, clearances, cable routes and server room layout |
| Network requirements | Bandwidth, latency and firewall openings required on the Government Wide Area Network, for the Purchaser to provision |

The ICT Site Preparation Guide is issued first, in week 4, because the facility works begin in week 7, build the server room first, and must build it to the guide. Everything else is completed together and reviewed with NRB as one design, so that an interface agreed with NRIS and a firewall rule in the Low-Level Design cannot disagree.

Process re-engineering. The Information System changes how cards move from request to dispatch. Each change is designed as a process, with its roles, controls and procedures, rather than left to be discovered by operators after go-live:

| Process | Future state |
| --- | --- |
| Request intake | Records released in NRIS are retrieved through a single gateway and checked against those already held, so a request cannot enter production twice. Records failing validation are held with a reason and reported back to NRIS |
| Production | Validated records are batched and assigned by an operator to either line, with automated balancing, in-line verification and in-job reproduction of rejected cards |
| Card accountability | Every blank is held against its serial number from delivery to issue or certified destruction, with reconciliation at the end of every shift |
| Mailing and dispatch | Cards are matched with carriers by card identifier, enveloped and batched by ordering office for dispatch |
| Status | Each defined status is published back to NRIS automatically, where it drives the document tracker and the SMS notification to the cardholder |

Outputs. Future-state process maps, the roles and separation of duties for each process, and draft Standard Operating Procedures. The procedures are refined through pilot production and become the operator training material under Section 3.

Approval. The design is presented to NRB in week 5 and approved in week 6. Where the review changes the design, the change is made before approval rather than carried as an open action into the build.

## Build, installation and integration

Build, weeks 3 to 16.

| Activity | Weeks | Detail |
| --- | --- | --- |
| Equipment manufacture | 3 to 12 | Two personalization systems and two mailing systems, ordered in week 2 and started on their standard configuration. The options fixed at design approval are fitted in weeks 11 and 12 |
| Blank card manufacture | 7 to 23 | To the approved card design. A first run in weeks 7 to 13 produces the five thousand specimen cards used for qualification and factory acceptance, and qualification cards reach the equipment factory by week 14 so that laser parameters are set on the actual card body. The first delivery of not less than 500,000 cards follows in weeks 14 to 18 and is shipped separately from the equipment. The remaining 1,500,000 are produced in weeks 19 to 23 and delivered by week 25 in shipments of not less than 500,000, so that all 2,000,000 cards are on site before commissioning begins in week 27 |
| ICT infrastructure | 3 to 13 | Ordered at mobilization in the quantities set out in System Architecture Section 9.4, configured to the approved Low-Level Design, and delivered direct to site |
| Application software | 3 to 16 | The components fully defined by the Technical Requirements, which depend on neither the NRIS interface nor the QR specification, are built from week 3. The NRIS-facing and signing components follow design approval from week 7. Built in iterations, each demonstrated to NRB, and tested against NRIS interface simulators generated from the Interface Control Documents |
| NRIS side of the interface | 7 to 22 | Built by NRB developers to the same Interface Control Documents, with a joint checkpoint every two weeks |

Factory acceptance, week 17. The equipment is accepted at the manufacturer's factory in the presence of the NRB delegation, on the actual blank card stock. The Printer Control Service is run against the equipment manufacturer's personalization control software during the same visit, so the boundary between the application and the equipment is proven before either is shipped. All data used at the factory is synthetic.

Installation and integration, weeks 15 to 26. Two tracks run on site. The ICT track starts when the server room is handed over, and the equipment track when the equipment arrives.

| Activity | Weeks |
| --- | --- |
| ICT infrastructure delivered, inspected on delivery and racked | 15 |
| Platform build: application and database clusters, storage array, directory, database, security stack, non-production environments | 16 |
| Hardware security module installed at the primary site. Document Signer key generated at a key ceremony witnessed by NRB, and the certificate signing request submitted to e-Government | 16 |
| Secondary environment deployed at the Blantyre disaster recovery data center, its hardware security module enrolled and the Document Signer key replicated to it, and replication established | 16 to 18 |
| Application deployed and integrated with the directory | 17 |
| Early integration with NRIS, each interface tested against the NRIS test environment as NRB delivers it | 18 to 22 |
| Pre-commissioning tests of the ICT estate, and performance and security testing | 19 to 21 |
| Equipment inspected on delivery, unpacked and placed | 21 |
| Equipment installed and commissioned by the manufacturer's engineers | 21 to 23 |
| Integration with NRIS completed against NRB's delivered side | 23 and 24 |
| Independent penetration testing of the full deployed configuration | 24 |
| Pre-commissioning tests of the equipment and integration, and user acceptance testing with NRIS stakeholders | 24 to 26 |
| Pilot production of 500 to 1,000 test cards, not issued to citizens | 26 |

The ICT track does not wait for the equipment. Starting it when the server room is handed over moves integration with NRIS five weeks earlier, takes the Document Signer certificate off the critical path, and leaves the weeks after the equipment arrives for the equipment alone. NRB technical staff shadow both tracks from week 15.

The key ceremony is held in week 16, as soon as the module at the primary site is installed, because the certificate it produces has an issuing time outside the plan's control. The certificate is expected by week 19, six weeks before pilot production needs it. The certificate signing request carries only the public key, and the private key never leaves the modules, as described in System Architecture Section 10.4.

The secondary environment is deployed in weeks 16 to 18, so that replication has run for eight weeks before operational acceptance tests the failover. It is deployed into the Purchaser's existing disaster recovery data center, as described in System Architecture Section 9.3.

## Transition to production

From pilot to live production. Pilot production in week 26 runs the full process on test records against the NRIS test environment, and its cards are destroyed under the secure destruction procedure rather than issued. Operational acceptance tests in weeks 27 to 30 also run against the NRIS test environment, as the Responses to Queries 003 require, and their cards are not issued to citizens. Live production on real NRIS records begins once Operational Acceptance is achieved, at the full contractual throughput.

One request, one facility. While the existing card printers remain in service, a request must be produced by one facility only. The Information System retrieves the records NRIS releases to it, and its own check prevents a record entering its queue twice, but it cannot see what an existing printer has already produced. The release of each request to the new facility is therefore marked in NRIS, and the existing middleware selection excludes those records. This is agreed with NRB in the Interface Control Documents and tested in pilot production, because a citizen issued two valid cards is an error that surfaces only after both have been dispatched.

Cutover. NRB decides when requests move to the new facility, and may move them by request type if it chooses: new issuance first, then replacements and reprints. The existing printers remain available until the sustained production stability test has passed, so that a failure during acceptance holds requests in NRIS rather than stopping card issuance.

Nothing is lost if production pauses. NRIS remains the system of record, and a request not yet retrieved stays there. A request retrieved but not produced is held in the queue with its state. A pause in the new facility delays cards and does not lose them.

Stabilization. Through the handover phase in weeks 31 and 32, resident engineers are present on every production shift and production is reviewed daily with NRB. Support then moves to the warranty model in Section 5, under the service levels in System Architecture Section 12.4.

## Dependencies on the Purchaser and other parties

The plan relies on the following inputs. Each is stated with the week it is needed, meaning available at the start of that week, so that a late input is visible as a schedule risk while there is still time to act on it.

| Input | Provided by | Needed by | Needed for |
| --- | --- | --- | --- |
| NRIS documentation: data dictionary, message formats, authentication, database platform, existing middleware | NRB | Week 2 | Discovery and interface design |
| Access to the NRIS test environment for data profiling | NRB | Week 3 | Discovery |
| Card design decisions in the joint redesign | NRB | Week 6 | Card manufacture from week 7 |
| QR code specification: signing protocol, data format and schema, and the encryption key material where the specification requires encryption | NRB | Week 6 | Data Preparation Service and Signing Service build |
| Document Signer certificate profile and certificate signing request procedure | e-Government | Week 6 | Signing Service design |
| Decision on the observation period for the final acceptance demonstration | NRB | Week 6 | Operational acceptance schedule |
| Design review and approval | NRB | Week 6 | Contract milestone, Detailed Design Approval |
| Nomination of the factory acceptance delegation | NRB | Week 12 | Factory acceptance in week 17 |
| Dedicated electrical connection to the facility live | NRB | Week 13 | Server room handover in week 14 |
| Server room handed over: sealed, powered through its UPS, cooled and cabled, to the ICT Site Preparation Guide | Facility works | Week 15 | ICT installation from week 15 |
| Technical trainee nominations against the recommended numbers in Section 3 | NRB | Week 15 | Shadowing from week 15 |
| Government Wide Area Network provisioned to the stated requirements at the Card Production Facility and the Blantyre data center | NRB and e-Government | Week 16 | Replication from week 16 and integration from week 18 |
| Access, floor space, power and cooling for the secondary environment's rack at the Blantyre disaster recovery data center | NRB | Week 16 | Secondary environment |
| Certificates for the System's interfaces and services, including the NRIS interface | e-Government | Week 16 | Platform build and the NRIS interface |
| Documents required from the Purchaser for customs clearance of goods consigned to NRB | NRB | Week 17 | Deliveries on site in week 20 |
| Staff addresses designated for alert emails and SMS messages, by type of alert | NRB | Week 17 | Alerting configuration, tested in the pre-commissioning tests of the ICT estate |
| Connectivity from the Card Production Facility to the NRIS test environment | NRB | Week 18 | Integration and pilot production |
| Each NRIS interface, as NRB builds it | NRB developers | From week 18 | Early integration |
| Production floor ready for installation, to the ICT Site Preparation Guide | Facility works | Week 20 | Equipment installation from week 21 |
| Secure blank card store ready, sized for the full 2,000,000 cards | Facility works | Week 20 | First card delivery on site in week 20 |
| NRB Security Operations Center integration details: the product it runs, the receiving endpoint and the events required | NRB | Week 25 | Integration of the facility's Security Operations Center with NRB's |
| User trainee nominations against the recommended numbers in Section 3 | NRB | Week 20 | Training from week 25 |
| NRIS side of the interface complete and ready for integration | NRB developers | Week 23 | Completion of integration |
| Document Signer certificate issued | e-Government | Week 26 | Pilot production in week 26 |
| Remote support access arrangement | NRB and e-Government | Week 26 | Warranty support |

The inputs among these on which the System's design relies are also set out in System Architecture Section 13.1.

## Responsibility assignment

R responsible for doing the work, A accountable for its completion, one per activity, C consulted before it is done, I informed of the outcome.

| Activity | Supplier | Equipment manufacturer | Card manufacturer | Facility works | NRB | e-Government |
| --- | --- | --- | --- | --- | --- | --- |
| Discovery and NRIS data analysis | A, R | I |  | C | C |  |
| High-Level and Low-Level Design | A, R | C |  | C | C | I |
| Card layout and card identifier | A, R | C | R |  | C |  |
| ICT Site Preparation Guide | A, R | C |  | C | I |  |
| Interface Control Documents | A, R |  |  |  | R |  |
| NRIS side of the interface | C |  |  |  | A, R |  |
| Application software build | A, R | C |  |  | I |  |
| Equipment manufacture and factory acceptance | A | R | C |  | C |  |
| Blank card manufacture and delivery | A |  | R |  | I |  |
| Qualification of the card body on the laser systems | A | R | R |  | I |  |
| Server room handover | C |  |  | A, R | I |  |
| Production floor ready for installation | C | C |  | A, R | I |  |
| Shipping, customs clearance and delivery | A, R | C | C |  | C |  |
| ICT infrastructure installation and platform build | A, R |  |  | C | I |  |
| Equipment installation and commissioning | A | R |  | C | I |  |
| Secondary environment at Blantyre | A, R |  |  |  | C |  |
| Government Wide Area Network provisioning | C |  |  |  | A, R | R |
| Document Signer key ceremony and certificate signing request | A, R |  |  |  | C | I |
| Document Signer certificate issue | C |  |  |  | I | A, R |
| Integration and user acceptance testing | A, R |  |  |  | R |  |
| Pre-commissioning tests and pilot production | A, R | R |  |  | C |  |
| Training delivery | A, R | R |  |  | C |  |
| Operational acceptance tests | R | C |  |  | A |  |
| Handover and transfer of Security Operations Center operation | A, R |  |  |  | C |  |

Operational acceptance is shown as the Purchaser's, because the Purchaser performs those tests with the Supplier's assistance under the Contract. Approval of contract deliverables rests with the Project Manager and is not repeated against each activity.

## Implementation risks and mitigation

Likelihood and impact are rated high, medium or low. Each risk has one owner, and the register is reviewed at every progress meeting from week 1.

| ID | Risk | Likelihood | Impact | Mitigation | Owner |
| --- | --- | --- | --- | --- | --- |
| R1 | The NRIS side of the interface is not complete when integration must finish in weeks 23 and 24 | Medium | High | Interface Control Documents agreed at design approval; production side proven against simulators from week 7; each interface integrated as NRB delivers it from week 18; joint checkpoint every two weeks; the approved database connection described in System Architecture Section 7.5 available as a fallback where the Purchaser approves it | Supplier, with NRB |
| R2 | The Document Signer certificate is not issued in time for pilot production in week 26 | Low | High | Certificate profile and procedure agreed with e-Government by week 6; key ceremony in week 16, six weeks before pilot production needs the certificate; issuing time confirmed in writing during design | Supplier, with e-Government |
| R3 | Throughput with the full personalization content falls short of 2,000 cards per hour across two lines | Medium | High | Throughput of not less than 1,000 cards per hour per machine with the full personalization content confirmed by the equipment manufacturer before order; throughput measured at factory acceptance on the actual card body; reject causes tracked from pilot production | Supplier, with the equipment manufacturer |
| R4 | The card body and the laser systems, supplied by two manufacturers, do not produce the required marking quality together | Medium | High | Qualification cards at the equipment factory by week 14; laser parameters set on the actual card body; factory acceptance run on production card stock | Supplier |
| R5 | The equipment is not ready for factory acceptance in week 17 | Low | High | Manufacture started on order in week 3, with the design options fitted after approval, giving four weeks of float; progress inspections during manufacture | Supplier, with the equipment manufacturer |
| R6 | Customs clearance extends beyond week 20 | Medium | High | Clearance documentation prepared during manufacture; clearing agent appointed by week 12; shipment arranged to arrive with time for clearance within the window; cards shipped separately with five weeks of float | Supplier |
| R7 | The server room is not handed over in week 14, or the production floor is not ready in week 20 | Medium | Medium | ICT Site Preparation Guide issued in week 4; server room built first; dedicated electrical connection needed by week 13; readiness inspection in week 18. A late server room moves the ICT track, which carries five weeks of float, and no milestone | Facility works |
| R8 | Government Wide Area Network capacity cannot sustain replication to Blantyre within the five minute lag | Medium | Medium | Network requirements issued in week 4; link measured before deployment; replication compressed and tuned; lag monitored from week 18 so a shortfall is known eight weeks before failover is tested | Supplier, with NRB and e-Government |
| R9 | NRIS records fail validation in numbers that disrupt production | Medium | Medium | Test data profiled during discovery; validation rules agreed at design; failing records held with a reason and reported to NRIS rather than printed | Supplier, with NRB |
| R10 | A request is produced by both the existing printers and the new facility during transition | Low | High | Release to the new facility marked in NRIS and excluded from the existing middleware selection; tested in pilot production | NRB, with the Supplier |
| R11 | Trained NRB staff are not available in the numbers needed for operational independence in operational acceptance | Medium | Medium | Recommended numbers and prerequisites issued in week 2; nominations by week 20; operator training completed first within the training window | NRB, with the Supplier |
| R12 | Remote access for the equipment manufacturer's specialists is not arranged by go-live | Low | Medium | Arrangement agreed with NRB and e-Government during design; resident engineers on site throughout stabilization | Supplier |

The risk that most threatens the schedule is R1, because the NRIS side of the interface is the one chain in Section 2.2 without float that runs through work outside the Supplier's control. The mitigation is to agree the interface early, prove the production side against simulators, and integrate each interface as it is delivered, so that a late or divergent interface is visible weeks before completing integration depends on it. R2, R5 and R7 sat on or beside the critical path; the separate ICT track and the early start of manufacture now give each of them float.

## Documentation deliverables

Every document the Information System requires is listed below with the week it is delivered, in the groupings of the Technical Requirements. Each is versioned, reviewed and approved before issue under the documentation control described in Section 4.7, and delivered in editable electronic format and as PDF. Documentation of the facility systems, including the physical layout drawings, facility floor plans and power and cooling design, and the electrical, UPS, generator, HVAC, fire suppression, access control, CCTV, structured cabling and raised floor records, is delivered under the facility works.

| Document | Content | Week |
| --- | --- | --- |
| Project Initiation Document, Information System part | Scope, workstreams, baseline schedule, the Purchaser's inputs and their dates, risks, and the governance of the Information System workstreams | 2 |
| Discovery Report | The findings of discovery and the decisions they require, as described in Section 2.3 | 4 |
| ICT Site Preparation Guide | What the facility works must provide for the Information System, as described in Section 2.4 | 4 |
| High-Level Design | Solution architecture, network architecture and data flow diagrams, and the security architecture | 5, approved 6 |
| Low-Level Design | Detailed system design, rack elevations, IP addressing scheme, VLAN, firewall and database configuration, parameter configuration sheets and firmware versions | 5, approved 6 |
| Integration documentation | Integration Strategy and Methodology, Detailed Integration Architecture, Interface Control Documents, API Specifications, and Data Mapping and Transformation Documents; As-Built Integration Documentation covering the API, web services and middleware configuration; third-party integration procedures for the postal operator and the Government PKI | 5; 16 |
| Security documentation | Security architecture, access control matrix, user roles and permissions matrix, encryption key management and PKI procedures, audit logging configuration, and the cybersecurity hardening guide | 5; 17 |
| Database and data management documentation | Database schema, data dictionary, backup and restore, replication and archiving procedures, and data retention policies | 5; 17 |
| Acceptance Test Procedures | Factory acceptance test procedure; Pre-Commissioning Test Program; operational acceptance test procedures | 14; 17; 24 |
| Test reports | Factory, site and user acceptance test reports, integration test plans, scripts and reports, test scripts and results, performance, stress and security test reports, and defect logs with their resolutions, as described in Section 4.7 | As each test completes, 17 to 30 |
| Equipment and device manuals | Manufacturers' operation, technical, preventive maintenance and spare parts manuals for the personalization and mailing equipment and the ICT hardware | With delivery, 15 and 20 |
| Installation and configuration documents | Hardware and software installation guides and configuration manuals | With installation, 15 to 23 |
| Business continuity and disaster recovery procedures | Recovery, backup restoration and failover procedures, emergency contacts and downtime management | 19 |
| User manuals | Card personalization software, card issuance, mailing system, quality assurance and inspection, card production workflow, reporting and dashboards, and system administration | 24 |
| Standard Operating Procedures | Card production, card printing, quality verification, dispatch and mailing, consumables replacement, daily start-up and shut-down, batch processing, escalation and incident reporting | Draft 5; final 24 |
| Training materials | Training manuals, presentations, practical exercise guides, quick reference guides, laboratory manuals, and videos where the task is easier shown than described | 24 |
| Administrator training materials | Administration guides and laboratory exercise guides for the technical training | 24 |
| Operational and maintenance checklists | Daily operational, preventive maintenance, backup verification, environmental monitoring and facility inspection checklists | 24 |
| Operation and maintenance manuals | Preventive maintenance manuals, troubleshooting guides, diagnostic and system recovery procedures | 24; final 30 |
| Training records | Attendance registers, training reports and the competence matrix described in Section 3.7 | As each course completes, 25 to 28 |
| Warranty and support documentation | Warranty certificates, support escalation matrix, service level documents and manufacturer support contacts | 30 |
| Asset and inventory documentation | Equipment inventory register, serial number records, asset tagging schedule and software license inventory | 30 |
| Compliance and certification documentation | Manufacturer certifications, compliance certificates, ISO compliance documentation, security compliance reports and regulatory approvals | 30 |
| As-built documentation | As-built architecture diagrams, final network topology, final equipment placement, deviations from the approved design, and final configuration baselines | From 27; final 32 |

Operating documents are delivered in week 24, before training begins in week 25, because the training teaches from them: an operator trained on the procedure that will be used in production does not have to learn it a second time.

# Training Sub-Plan

## Approach and knowledge transfer

Training covers the Information System as supplied: the personalization and mailing equipment, the application software, the integration with NRIS, and the ICT infrastructure and security components that support them. Training on the facility systems, including the power, HVAC, fire suppression and physical security installations, is delivered under the facility works.

The aim is that NRB staff operate, administer and give first-line support to the system without the Supplier. Operational independence is tested at operational acceptance, and the training is built backwards from that test: every task a member of NRB staff must perform unaided at acceptance is taught, practiced and assessed before it.

Knowledge transfer is a progression, not a course. Responsibility moves from the Supplier to NRB in stages, and each stage has a condition that must be met before the next begins.

| Stage | Weeks | Who leads | What NRB staff do | Condition to move on |
| --- | --- | --- | --- | --- |
| Factory training | 17 | Equipment manufacturer | Technical staff in the factory acceptance delegation learn the equipment where it is built, alongside its engineers | Equipment operation, calibration and first-line maintenance demonstrated at the factory |
| Shadowing | 15 to 26 | Supplier | Technical staff work alongside the engineers installing, configuring and commissioning the system | Participation recorded against each installation activity |
| Formal training | 25 to 28 | Supplier, then NRB trainers under observation | Classroom, laboratory and hands-on training on the deployed system, by role | Each trainee assessed as competent for their role, Section 3.7 |
| Coaching in production | 27 to 28 | NRB staff, coached by the Supplier | NRB staff operate production during the operational acceptance tests, with Supplier engineers beside them | Two shifts run without Supplier intervention |
| Independent operation | 28 onward | NRB staff | NRB staff operate the whole system, with the Supplier observing only | Operational independence demonstrated in operational acceptance test 16 |

Train the trainer. NRB designates trainers from among the trainees, and they are certified to train further staff. User-stream trainers learn their stream as trainees, then deliver it to the cover group under observation. Technical-stream trainers, who will already have been through factory training and shadowing, co-deliver the technical training alongside the Supplier's trainers. Each is certified on the observed delivery. A trainer who has taught a class under observation has shown the thing certification is meant to establish.

## Recommended trainees and prerequisites

The numbers below are derived from how the facility runs: two personalization lines and two mailing lines, operated across two shifts of seven hours. They state the minimum needed to operate, and the number recommended for training so that every role has cover.

User training.

| Role | Posts per shift | Minimum to operate two shifts | Recommended to train |
| --- | --- | --- | --- |
| Card personalization operator | 2, one per line | 4 | 6 |
| Mailing and dispatch officer | 2, one per line | 4 | 6 |
| Quality assurance staff | 1 | 2 | 3 |
| Card issuance officer, including blank card stock | 1 | 2 | 3 |
| Supervisor | 1 | 2 | 3 |
| Helpdesk and frontline support | 1 | 2 | 3 |
| Total | 8 | 16 | 24 |

Three people are trained for every post that is staffed on both shifts: one for each shift, and one to cover leave, sickness and rotation. The supervisor and the card issuance officer on each shift are also the two custodians needed for the secure destruction of rejected cards, so both shifts can close out their own rejects.

Technical training.

| Role | Minimum | Recommended to train |
| --- | --- | --- |
| System administrator | 2 | 3 |
| Database administrator | 1 | 2 |
| Network engineer | 1 | 2 |
| Security engineer | 2 | 3 |
| Infrastructure engineer | 1 | 2 |
| Technical support, equipment first-line maintenance | 2, one per shift | 3 |
| Total | 9 | 15 |

No technical role is held by one trained person. A system that one person knows how to administer stops being administrable when that person is on leave.

Management training. Nine participants are recommended: two from executive leadership, two operations managers, and one each of ICT, security and facility management, with two from audit and compliance.

Trainers. Six trainers are recommended for certification, drawn from the trainees above rather than in addition to them: four from the user stream, one for each of personalization, mailing and dispatch, quality and issuance, and supervision and helpdesk; and two from the technical stream.

Prerequisites.

| Role | Prerequisite |
| --- | --- |
| All user roles | Secondary education, basic computer literacy, the ability to work to written procedures, and clearance to the Purchaser's standard for access to citizen data and secure card stock |
| Supervisor | As above, with supervisory experience |
| Helpdesk and frontline support | As above, with experience of desktop support |
| System administrator | Degree or diploma in information technology, with Windows Server administration experience |
| Database administrator | Degree or diploma in information technology, with SQL Server administration experience |
| Network engineer | Degree or diploma in information technology or engineering, with network experience at the level of Cisco CCNA |
| Security engineer | Degree or diploma in information technology or information security, with experience of security monitoring |
| Infrastructure engineer | Degree or diploma in information technology or engineering, with server, storage and virtualization experience |
| Technical support, equipment | Technician qualification in electrical, electronic or mechanical engineering |
| Trainers | The prerequisites of their stream, with experience of instructing others |

## User training

Participants. Card personalization operators, card issuance officers, quality assurance staff, mailing and dispatch officers, helpdesk and frontline support staff, and supervisors.

Curriculum. Training is role-based. Every trainee takes the common modules, and each role takes the modules its work requires. O operator, M mailing and dispatch, Q quality assurance, I card issuance, S supervisor, H helpdesk.

| Module | Content | Days | Roles |
| --- | --- | --- | --- |
| System overview | The path of a card from the NRIS request to dispatch, the part each role plays in it, and what each console does | 0.5 | All |
| Card personalization operations | Loading blank stock, assigning jobs to a line, monitoring production, reject handling and in-job reproduction, assisting calibration, emergency stops | 2 | O, S |
| Mailing system operations | Loading carriers and envelopes, card-to-carrier matching, reject magazines, dispatch batching by ordering office, dispatch records | 2 | M, S |
| Card issuance workflow | Releasing batches, reprint and replacement requests, records held at validation, the exception queue | 1 | I, S |
| Quality assurance procedures | Reading verification results, inspecting security features, reject decisions, reject trends by cause | 1 | Q, O |
| Routine operations | Daily start-up and shut-down, consumables, shift handover, blank card issue and return, end-of-shift reconciliation, secure destruction under dual custody | 1 | All |
| Security and compliance | Handling citizen data, access rules, secure stock, what must be reported and to whom | 0.5 | All |
| Reporting | Production, issuance, rejection and service level reports and dashboards | 0.5 | S, I, Q, H |
| Helpdesk and first-line support | Logging incidents, assigning severity, first-line checks, escalation to the Supplier | 1 | H |
| Scenarios and supervised production | Simulated faults and exceptions: a card that cannot be matched, a stock discrepancy, a cancellation arriving mid-job, a line stopping mid-batch. Then pilot production, run by the trainees under supervision | 2 | All |

An operator's path is seven days, and a supervisor's, the longest, is nine and a half, within the two weeks allowed.

Pilot production is run by the trainees. The pilot run in week 26 is operated by the operators being trained, under supervision. The first cards the lines produce for the record are produced by the people who will operate them, and pilot production doubles as their practical assessment.

Mode. Classroom-based theoretical training, hands-on practical training on the deployed system, live production environment demonstrations, scenario-based simulations, and on-the-job operational coaching through operational acceptance.

Materials. User manuals, Standard Operating Procedures, quick reference guides for each console, presentation slides, practical exercise manuals, video tutorials for the equipment tasks that are easier shown than described, assessment tests, attendance registers and training reports. All are in English, and delivered in editable electronic format and as PDF.

## Technical training

Participants. System administrators, database administrators, network engineers, security engineers, infrastructure engineers and technical support staff.

Curriculum. SA system administrator, DB database administrator, NE network engineer, SE security engineer, IE infrastructure engineer, TS technical support.

| Module | Content | Days | Roles |
| --- | --- | --- | --- |
| System architecture | Components, network zones, data flows, high availability and the secondary environment | 1 | All |
| Hardware administration | Virtualization hosts, the storage array, hardware security modules, workstations, and first-line maintenance of the personalization and mailing equipment | 1 | IE, TS |
| Software administration | Application services, configuration, releases and change control | 1 | SA, TS |
| Database administration | SQL Server administration, replication to the secondary environment, backup, restore and point in time recovery | 2 | DB |
| Network and infrastructure | Zones and VLANs, firewall policy, the Government Wide Area Network links, the storage network, the Hyper-V clusters, the standalone host at the secondary site and the storage array | 2 | NE, IE, SE |
| Security administration | Access control and privileged access, hardware security module operation and key lifecycle, security monitoring, Security Operations Center procedures, incident handling | 2 | SE, SA |
| Integration and APIs | The NRIS interface and its Interface Control Documents, monitoring exchanges, exceptions and retries | 1 | SA, DB |
| Troubleshooting and support | Diagnostics, log analysis, event correlation, escalation, and fault simulations on the training environment | 2 | All |
| Performance monitoring | Dashboards, capacity tracking, alert thresholds | 0.5 | SA, IE, NE |
| Backup, recovery and failover | Restoration drills on the training environment, and the failover procedures for the cluster and the secondary environment | 1 | SA, DB, IE |

Specialists take the depth of their own field, and the system administrator takes what is needed to oversee the rest. The longest path, the system administrator's, is eight and a half days, within the two weeks allowed.

Equipment training at the factory. Technical support staff and infrastructure engineers in the factory acceptance delegation are trained by the equipment manufacturer on equipment operation, calibration, preventive maintenance and first-line repair during the factory acceptance visit in week 17. Travel and boarding for the delegation are borne by the Government of Malawi under the Contract.

Fault simulation is taught on the real platform. Faults are induced in the training environment, which runs the same software and versions as production: a service stopped, a certificate near expiry, an NRIS exchange failing and retrying. The loss of a host and a database failover are performed for real in the failover tests before commissioning, which technical trainees attend while shadowing. Administrators who have only read a recovery procedure meet the fault for the first time in production. Administrators who have performed it meet it for the second time.

Mode. Advanced classroom technical training, hands-on laboratory sessions, equipment training by the manufacturer, practical troubleshooting workshops, live administration sessions on the production system for critical technical staff, shadow support during installation and commissioning, and knowledge transfer sessions.

Materials. Technical manuals, administration guides, installation manuals, configuration guides, as-built documentation, network diagrams, troubleshooting manuals, maintenance procedures, laboratory exercise guides and configuration backup templates, in editable electronic format and as PDF.

## Management training

Participants. Executive leadership, operations managers, ICT managers, security managers, facility managers, and audit and compliance personnel.

Curriculum. Management training concerns oversight, governance and sustainability rather than operation.

| Module | Content |
| --- | --- |
| Solution overview | What the facility produces, how, and where its limits are |
| Governance and operations | Roles, separation of duties, approvals and change control |
| Security and compliance | Data protection obligations, custody of the signing key, incident reporting obligations |
| Performance and reporting | Production, quality and service level dashboards, and what each measure means |
| Business continuity | Failover and recovery, what the secondary environment covers and what it does not, and who decides |
| Maintenance and lifecycle | Warranty and post-warranty support, spare parts, releases, and renewal of the Document Signer certificate |
| Audit and compliance | Audit trails, stock reconciliation, destruction certificates, and how each is inspected |

Mode and duration. A half-day executive briefing with presentations, and two days of strategy sessions, workshops and facilitated sessions for managers. Executive sessions may be held virtually where appropriate.

Materials. Executive briefing materials, governance manuals, operational dashboards, service level templates, risk management documentation, business continuity documentation and strategic operational guides.

## Schedule, location and training environment

Schedule.

| Week | Activity |
| --- | --- |
| 2 | Recommended trainee numbers and prerequisites issued to NRB |
| 15 | Technical trainee nominations received from NRB |
| 15 to 26 | Technical staff shadow installation and commissioning, from the start of the ICT installation |
| 17 | Equipment training for the factory acceptance delegation |
| 20 | User trainee nominations received from NRB |
| 25 and 26 | User training, groups one and two, one for each shift, run in parallel. NRB user-stream trainers train in these groups |
| 26 | Pilot production run by the trainees under supervision |
| 26 | Management training |
| 26 and 27 | Technical training, with NRB technical trainers co-delivering |
| 27 and 28 | User training, cover group, delivered by NRB trainers under observation |
| 28 | Operational independence, operational acceptance test 16 |

The order is deliberate. Operators are trained first, so that the two shifts can run the sustained production test from week 27 and NRB staff can demonstrate independence in week 28, before the final acceptance demonstration in weeks 29 and 30 described in Section 2.2.

Location.

| Training | Location |
| --- | --- |
| User classroom sessions | The training facilities provided by the Government of Malawi, or on site at the Card Production Facility |
| User hands-on training | On the deployed system at the Card Production Facility |
| Technical classroom and laboratory | On site, using the training environment |
| Live administration sessions | On the production system, for critical technical staff |
| Equipment training | At the equipment manufacturer's facility during factory acceptance, and on site |
| Management training | At NRB headquarters, on site, or at executive conference facilities, and virtually where appropriate |

Training environment. A dedicated training environment runs as isolated virtual machines on the platform described in System Architecture Section 9.1, on its own network segment, with the same software and versions as production. It holds masked data rather than citizen records, as described in System Architecture Section 10.2, so trainees can practice on realistic records, and faults can be induced, without either touching real citizen data.

Training cards are accounted for. Cards used in hands-on training are issued from controlled stock against their serial numbers and destroyed under dual custody, as described in System Architecture Section 6.10, so training leaves the stock reconciliation as complete as production does.

## Assessment, certification and operational independence

Assessment. Every trainee is assessed on the tasks their role performs, not only on what they remember.

| Assessment | Method | Standard |
| --- | --- | --- |
| Knowledge | Written test at the end of each stream | Pass mark of 70 percent |
| Competence | Each task in the role's competence list performed unaided on the deployed system | Every task passed |
| Trainer | Delivery under observation: the cover group for user-stream trainers, technical sessions for technical-stream trainers | Delivered to the standard of the Supplier's own trainers |

A trainee who does not pass is retrained on the tasks concerned and assessed again.

Competence matrix. For every trainee, the tasks of their role are recorded as assessed competent, with the date and the assessor. The matrix is handed to NRB with the training reports, so the Purchaser knows before operational acceptance which of its staff can perform which task, and where cover is thin.

Certificates. Each trainee assessed competent receives a certificate of competence for their role. Each trainer who passes the observed session receives a trainer certificate for their stream.

Records. Attendance registers are kept for every session, and a training report is issued for every course, with attendance, assessment results and any retraining, in editable format and as PDF.

Operational independence is the final test of the training. Two operational acceptance tests measure whether it worked:

| Test | What it requires of NRB staff |
| --- | --- |
| 13, multi-shift operation | Two shifts run production with consistent throughput, shift handover completes without disruption, and nothing depends on the Supplier being present |
| 16, operational independence | NRB staff operate the full system, perform every routine task and handle minor faults, with the Supplier observing only, and the operational manuals prove usable |

The training is judged by those results rather than by the courses delivered. Where either test shows a gap, the tasks concerned are retrained and the test is repeated.

## Supplier trainers and sample materials

Supplier trainers. Training is delivered by members of the Supplier's technical team, each teaching the field they install and support, and by the equipment manufacturer's certified trainers for the equipment. Each holds at least the qualifications below, and their curricula vitae and certificates are provided with the key personnel.

| Trainer | Delivers | Qualification and experience |
| --- | --- | --- |
| Training and Change Management Specialist | Leads the program: training needs, curricula, train the trainer, assessment and certification, and the management workshops | Degree in ICT, education or human resource development; at least five years delivering ICT training to government staff, operators and technical administrators |
| Equipment manufacturer's certified trainers | Equipment operation, calibration, preventive maintenance and first-line repair, at the factory and on site | Certified by the manufacturer to train on the personalization and mailing systems supplied |
| Secure Personalization System Engineer | Card personalization operations, reject handling and calibration | Bachelor's degree in computer, electronics or mechatronics engineering; at least five years on large-scale polycarbonate card personalization and laser engraving; manufacturer certification on the personalization system supplied |
| Card Mailing System Engineer | Mailing system operations and dispatch | Bachelor's degree in IT, computer, electronics or mechatronics engineering; at least five years on ID card mailing and dispatch systems |
| ID Card Security Specialist | Quality assurance procedures and the inspection of card security features | Degree or diploma in computer science or information security; experience in secure ID card and secure document programs |
| Card Production Facility Infrastructure Engineer | Hardware administration, the clusters and the storage array, database administration, backup, recovery and failover | Degree in computer engineering, IT or electrical engineering; relevant manufacturer certifications; at least five years in data center and high availability systems |
| Network Engineer | Zones and VLANs, firewall policy and the wide area network links | Degree or diploma in computer science, network engineering or telecommunications; CCNA and CCNP; at least five years on VLANs, firewalls and secure government networks |
| Cybersecurity and PKI Specialist | Security administration, hardware security module operation and key lifecycle, security monitoring and incident handling | Degree in cybersecurity, computer science or information security; experience with hardware security modules, encryption and digital certificates |
| Software Integration Specialist | Software administration, the NRIS interface, integration and APIs | Degree in computer science, software engineering or information systems; at least five years in enterprise systems integration |

Sample module outline. Every module is prepared to the same pattern. Card personalization operations, the two-day module for operators and supervisors in Section 3.3, is set out below as it is delivered.

| Session | Content | Practical exercise on the deployed system |
| --- | --- | --- |
| Day 1, morning | The personalization line: feeder, laser stations, verification, reject module and stacker; emergency stops and safe working; the Printer Controller Admin console | Walk the line at rest, locate every emergency stop, and identify each module and its status on the console |
| Day 1, afternoon | Blank card stock: issue against serial numbers, loading the feeder, returning unused blanks; selecting a prepared batch and assigning it to a line | Issue blanks to a training job, load them, assign the job to a line and start it |
| Day 2, morning | Monitoring production: batch progress, line status and reject reasons; taking a laser station out of service between runs; assisting calibration | Take a station out of service at the end of a run, restart production with the job settings for the remaining stations, and read the calibration log |
| Day 2, afternoon | Rejects and reconciliation: in-job reproduction, quarantine of rejected cards, closing a batch against its reconciliation; shift handover | Resolve a seeded reject, close the batch with every blank accounted for, and hand over to the next shift |

At the end of the module the trainee performs each task in the operator's competence list on the deployed system without help.

Sample competence record. The record kept for each trainee, shown for the card personalization operator:

| Task | Standard |
| --- | --- |
| Issue blank cards to a job and load the feeder | Every blank issued against its serial number, and the count agrees with the job |
| Assign a prepared batch to a line and start production | Correct batch on the correct line, started without assistance |
| Respond to a laser station out of service | The run is concluded, production resumes on the remaining stations or on the other line, and the event is reported to the supervisor |
| Handle a rejected card | Card quarantined against its serial number, and its reproduction confirmed within the job |
| Close a batch | Closed only with every blank accounted for, and any discrepancy raised |
| Stop the line safely | Emergency stop reached and operated from the working position, and the restart follows the procedure |
| Hand over the shift | Handover record complete, and open issues passed on |

For each task the record holds the assessor, the date and the result, competent or retrain, and it feeds the competence matrix described in Section 3.7.

# Testing and Quality Assurance Sub-Plan

## Test strategy and levels

Testing is arranged in levels, and each level proves something the next one relies on. A defect is cheapest to correct at the level where it first appears, so each level is designed to find its own class of defect before the next begins. The Purchaser's acceptance tests confirm a system that has already been tested. They are not where its defects are first found.

| Level | What it proves | Where | Weeks | Performed by | Output |
| --- | --- | --- | --- | --- | --- |
| Development testing | Each component meets its design, and passes code review and static and dynamic security testing | Supplier's development environment | 7 to 16 | Supplier | Test records and release gate results |
| Interface testing against simulators | The production side of the NRIS interface conforms to the Interface Control Documents | Staging environment | 9 to 16 | Supplier | Interface test results |
| Factory acceptance testing | The equipment meets its specification on the actual card stock, and works with the application | Equipment manufacturer's facility | 17 | Supplier and equipment manufacturer, witnessed by NRB | Factory Acceptance Test report |
| Inspection on delivery | Goods arrived complete, undamaged and as ordered | Card Production Facility | 15 for the ICT infrastructure, 21 for the equipment | Supplier, with NRB | Delivery inspection record |
| Integration testing | The system works with NRIS and meets its performance and security requirements | Card Production Facility, against the NRIS test environment | 18 to 26 | Supplier, with NRB developers | Integration, performance and security test reports |
| User acceptance testing | Business workflows, functions and reports are acceptable to NRIS stakeholders | Card Production Facility | 24 and 25 | NRB stakeholders, supported by the Supplier | User Acceptance Test report |
| Pre-commissioning tests | The installed system is ready for the Installation Certificate | Card Production Facility | 19 to 26 | Supplier, with the Purchaser's assistance | The Table A reports |
| Operational acceptance tests | The system operates in production conditions, and NRB operates it | Card Production Facility, against the NRIS test environment | 27 to 30 | Purchaser, with the Supplier's assistance | The Table B reports |
| Continuing assurance | The system remains secure and recoverable | Card Production Facility | After acceptance | Supplier, and an independent party for penetration testing | Vulnerability, penetration and disaster recovery test reports |

Inspection on delivery. Each delivery is checked against the packing list and the purchase order, and its packaging and shock indicators are checked for damage. Serial numbers are recorded at receipt. A shortage, a discrepancy or damage is recorded, photographed and reported for replacement, and the item is held aside until it is resolved. NRB signs the delivery inspection record before installation begins.

Entry and exit. A level begins only when the level before it has met its exit condition, and no level exits with a critical or major defect open, as defined in Section 4.7. Each level ends with a report, and the Purchaser's approval of the report is the record that the level is complete.

Every requirement is traced to a test. Each technical requirement is mapped to the test or tests that verify it, and the mapping is maintained through every level. Acceptance therefore demonstrates every requirement, rather than the requirements that happened to fall within a test someone thought to write.

## Test environments and test data

| Environment | Location | Used for | Data |
| --- | --- | --- | --- |
| Development | Supplier's facility | Build, development testing | Synthetic |
| Staging | Supplier's facility | Interface testing against simulators, integration before factory acceptance | Synthetic |
| Factory | Equipment manufacturer's facility | Factory acceptance testing | Synthetic, on the actual card stock |
| User acceptance testing | Non-production segment of the platform at the Card Production Facility | Integration testing and user acceptance testing | Records from the NRIS test environment |
| Training | Non-production segment of the platform at the Card Production Facility | Training under Section 3, and fault simulation | Masked |
| Production | Card Production Facility and the secondary environment | Pre-commissioning and operational acceptance, against the NRIS test environment, then live operation after Operational Acceptance | Test records, then live records |

The non-production environments are described in System Architecture Section 9.1. The NRIS test environment is provided by the Purchaser, and connectivity to it from the Card Production Facility is among the inputs dated in Section 2.7.

Citizen data stays in Malawi. Every test performed away from Malawi uses synthetic data, as set out in Section 1.2. Citizen data enters testing only on the installed system, and in the non-production environments only in masked form.

Test cards are accounted for. Every card used in factory acceptance, in pilot production and in testing on site is issued from controlled stock against its serial number, and destroyed under dual custody as described in System Architecture Section 6.10. Test cards are never issued to citizens, and testing leaves the stock reconciliation as complete as production does.

## Factory acceptance testing

When and where. Week 17, at the equipment manufacturer's production facility, witnessed by the NRB delegation. The factory acceptance test procedure is issued to NRB for approval in week 14, so that the delegation arrives knowing what will be tested and what passing means.

What is tested.

| Area | Test |
| --- | --- |
| Laser personalization features | Laser engraved text, greyscale portrait, secondary image, micro-lettering, CLI, the QR code with both alphanumeric values, and tactile laser printing, all on the actual card body |
| Marking resolution | Portrait at 600 dpi or higher in greyscale, and micro text at 600 dpi or higher at a line width and height of 0.33 mm, measured on the produced cards |
| Laser stations | The five stations, two for each face and one for the CLI. A station for one face is switched off and taken out of operation at the end of a run, and production resumes on the remaining stations once the job settings are reconfigured |
| Throughput | The contractual rate in System Architecture Section 3.5, not less than 1,000 cards per hour on each personalization system, with the full personalization content |
| Card recognition and verification | Recognition of the blank card body, X-Y alignment of front, back and CLI, in-line verification, rejection and in-job reproduction |
| Calibration | Calibration of individual stations and of all stations together, with the audit log it produces |
| Mailing and dispatch | One to four cards per carrier, card-to-carrier matching by card identifier, 1D, 2D and QR code verification, reject magazines, buffer modules and rate |
| Application boundary | The Printer Control Service submitting jobs to the equipment manufacturer's personalization control software and receiving results back |
| Safety and conformity | Emergency stops, noise level, and the electrical and environmental conformity documents |

Why the actual card body. The laser systems and the card come from two manufacturers. Marking quality depends on how that laser marks that card body, so a factory acceptance test run on another manufacturer's blanks would prove the wrong combination. Qualification cards reach the factory in week 14 so that laser parameters are set on the actual card before the test, as scheduled in Section 2.5.

Exit. The Factory Acceptance Test report is signed by the NRB delegation. Equipment ships only with no critical or major defect open. A minor defect is recorded with the date by which it will be corrected on site. All data used at the factory is synthetic.

## Integration and security testing

What each integration test covers is set out in System Architecture Section 7.16. The plan for performing them is as follows:

| Test | Weeks | Conditions | Performed with |
| --- | --- | --- | --- |
| Interface testing against simulators | 9 to 16 | Staging, simulators generated from the Interface Control Documents | Supplier |
| Interface testing against NRIS | 18 to 24 | NRIS test environment, each interface as NRB delivers it | NRB developers |
| System integration testing | 23 and 24 | End to end, with exceptions induced | NRB developers |
| Performance testing | 20 and 21 | Production platform | Supplier |
| Security testing | 20 and 21 | Vulnerability assessment, authentication testing, encryption validation | Supplier |
| Independent penetration testing | 24 | The full deployed configuration, including the Machine Control Zone | Independent third party |
| User acceptance testing | 24 and 25 | NRIS stakeholders, against the live integration | NRB, supported by the Supplier |

Penetration testing is independent and comes early enough to act on. The initial full penetration test is performed by an independent third party in week 24, once the equipment and its Machine Control Zone are installed, so that the whole deployed configuration is tested. Findings are corrected and retested in weeks 25 and 26, before the security operations acceptance test in week 27, which requires that no critical vulnerability remains. Penetration testing is repeated annually and vulnerability assessment at least quarterly, as described in System Architecture Section 10.5.

Performance is verified by the methods in System Architecture Section 11.6: throughput benchmarks, load testing against the response time thresholds, stress testing of concurrent users to 100 and beyond, transaction integrity at peak, and a sustained operation test.

Failover is tested by failing it. An application host and a database host are each removed while production runs, and the recovery targets for the loss of a host are measured. The database and the service virtual machines are then failed over to the secondary environment, and the recovery point and recovery time it achieves are measured, rather than checked by inspection of the configuration. It is rehearsed in pre-commissioning, repeated in operational acceptance, and tested at least annually thereafter, as described in System Architecture Section 9.3.

Deliverables. Test plans and test scripts, integration test reports, performance test reports, stress test reports, security test reports and the User Acceptance Test report.

## Pre-commissioning tests

The Pre-Commissioning Test Program is submitted to NRB for approval in week 17, and the tests run in weeks 19 to 26: those of the ICT estate from week 19, and those that need the equipment from week 24. They are performed by the Supplier with the Purchaser's assistance, and their successful completion is the condition for the Installation Certificate.

| # | Test | Scope | Week | Deliverable |
| --- | --- | --- | --- | --- |
| 1 | Physical installation verification | Placement and anchoring of the equipment, racks and workstations, cable management and labeling, and safety clearances. Building-level items are verified with the facility works | 24 | Physical Installation Verification Report |
| 2 | Electrical power | Performed under the facility works. The Information System relies on its result |  |  |
| 3 | Environmental systems | Performed under the facility works. The Information System relies on its result |  |  |
| 4 | Network infrastructure | LAN and WAN connectivity, redundancy, switch function, throughput, latency, VLANs, DNS and DHCP | 19 | Network Acceptance Report |
| 5 | Cybersecurity and access control | Active Directory integration, role-based access, password policy, firewall rules, anti-malware, endpoint protection, log generation and event monitoring | 19 | Security Readiness Report |
| 6 | Personalization equipment | Hopper loading and feeding, image, text and variable data engraving, alignment and greyscale consistency, QR encoding, barcode encoding where applicable, and print quality | 24 | Equipment Functional Test Report |
| 7 | Mailing system | Envelope feeding and insertion, address printing, sorting and batch processing | 24 | Mailing System Functional Test Report |
| 8 | Software installation and configuration | Operating systems, database, application, license verification, backup configuration and monitoring tools | 19 | Software Readiness Report |
| 9 | NRIS integration | Interface connectivity, secure communication, retrieval of demographic data, photograph and signature, status updates, and invalid record, missing data and communication failure handling | 25 | NRIS Integration Test Report |
| 10 | Data validation and integrity | Field mapping, transformation, character encoding, completeness and duplicate record detection | 25 | Data Integrity Verification Report |
| 11 | Card security features | Laser engraving quality, secondary image, micro text, guilloche, security background, UV features and machine-readable elements | 25 | Card Security Features Verification Report |
| 12 | Quality control system | Automated inspection, defect detection, OCR, barcode and image quality verification | 25 | Quality Assurance Test Report |
| 13 | Backup and recovery | Backup execution, database and configuration restoration, and the disaster recovery procedures, including failover to the secondary environment | 20 | Backup and Recovery Test Report |
| 14 | Production workflow simulation | Record retrieval from NRIS, job generation, personalization, quality inspection, mailing preparation, dispatch generation and status update to NRIS | 25 | Workflow Simulation Report |
| 15 | Pilot production readiness | 500 to 1,000 test cards produced through the actual production process | 26 | Pilot Production Readiness Report |
| 16 | Performance and capacity | Sustained and peak production rates in accepted finished cards, batch processing and mailing throughput | 26 | Capacity and Performance Test Report |

Pilot production. The pilot run produces between 500 and 1,000 test cards from records in the NRIS test environment, through the full process from retrieval to dispatch record and status update. It is operated by the operators being trained, as described in Section 3.3. It verifies data accuracy, print and engraving quality, mailing and reporting, and the sample card images required by the Technical Requirements are submitted again from its production. The cards are not issued, and are destroyed under dual custody.

Failure and retest. A test that fails is corrected and repeated at no cost to the Purchaser, and any test whose result the correction could affect is repeated with it.

## Operational acceptance tests

The operational acceptance tests are performed by the Purchaser with the Supplier's assistance, in the production environment against the NRIS test environment, as the Responses to Queries 003 require, once the Installation Certificate has been issued. Cards produced during the tests are not issued to citizens. Their successful completion is the condition for the Operational Acceptance Certificate.

No test is performed for the first time at acceptance. Each operational acceptance test has already been rehearsed in pre-commissioning, so that acceptance confirms a known result.

| # | Test | Principal success criteria | Weeks | Rehearsed in |
| --- | --- | --- | --- | --- |
| 1 | End-to-end workflow | All test records processed end to end without manual intervention, with status in NRIS and a full audit trail | 27 | Pre-commissioning 14 |
| 2 | Sustained production stability | Continuous operation over the defined period, availability of not less than 99 percent, no severity 1 failure | 27 and 28 | Pre-commissioning 16 |
| 3 | Production throughput | Contractual accepted finished cards per hour and mail items per hour achieved, with no backlog | 27 | Pre-commissioning 16 |
| 4 | Peak load | No failure or data loss, response times within thresholds, throughput not less than 95 percent of the nominal capacity, which is the contractual rate in System Architecture Section 3.5 | 27 | Performance testing |
| 5 | Data accuracy and integrity | Not less than 99.99 percent accuracy of data on cards, no mismatch with NRIS, no loss or duplication | 27 | Pre-commissioning 10 |
| 6 | NRIS business process integration | New issuance, reprint, replacement, and lost and damaged card processing, with no failed or orphaned transactions | 27 | Pre-commissioning 9 |
| 7 | Card quality and security | Full compliance with the approved design, security features correctly applied, reject rate not more than 1 percent | 27 | Pre-commissioning 11 and 15 |
| 8 | Mailing and dispatch | Not less than 99.5 percent accuracy in insertion and addressing, correct card-to-envelope-to-recipient matching | 27 | Pre-commissioning 7 and 15 |
| 9 | Audit trail and traceability | Full traceability from NRIS record to dispatch, all user actions and events logged and tamper-proof | 27 | Pre-commissioning 14 |
| 10 | Security operations | Access limited to authorized users, failed logins alerted, no privilege escalation, no critical vulnerability | 27 | Pre-commissioning 5 and penetration testing |
| 11 | Backup, restore and recovery | Backup during live operation and restoration without corruption or significant disruption | 27 | Pre-commissioning 13 |
| 12 | Monitoring and alerting | Alerts for failures, degradation and consumable thresholds received in real time | 27 | Pre-commissioning 8 |
| 13 | Multi-shift operation | Two shifts, handover without disruption, consistent throughput, no dependency on the Supplier | 27 and 28 | Training, Section 3 |
| 14 | Consumables and inventory | Accurate consumption tracking, low stock alerts, no stoppage for want of stock | 27 | Pilot production |
| 15 | Reporting and service levels | Daily, weekly and monthly reports, service level measures calculated correctly, no discrepancy between logs and reports | 27 | Pilot production |
| 16 | Operational independence | NRB staff operate the full system with the Supplier observing only | 28 | Training, Section 3.7 |
| 17 | Final operational acceptance demonstration | Continuous production over the agreed observation period with availability of not less than 99 percent, data accuracy not less than 99.99 percent, reject rate not more than 1 percent and mailing accuracy not less than 99.5 percent | 29 and 30 | All of the above |

How the measures are taken. Each success criterion is measured the same way throughout, and the method is agreed with NRB in the operational acceptance test procedures before the tests begin:

| Measure | Basis |
| --- | --- |
| Throughput | Cards per hour, across the two production lines, over the fourteen hour operating day |
| Reject rate | Cards rejected as a proportion of cards attempted |
| Data accuracy | Data on the produced cards, as read by in-line verification, compared with the NRIS source record |
| Mailing accuracy | Mail pieces correctly matched and addressed, as a proportion of mail pieces produced |
| Availability | Measured with the exclusions set out in System Architecture Section 9.3 |

The observation period. The final demonstration is planned on an observation period of ten working days in weeks 29 and 30, as set out in Section 2.2, with the period agreed at design approval.

## Defect management and quality assurance

Defect classification. Defects found in testing are classified by their effect on acceptance:

| Class | Definition | Rule |
| --- | --- | --- |
| Critical | Stops a test, corrupts or loses data, produces an incorrect card, or opens a security exposure | Corrected before testing continues |
| Major | Causes a success criterion to be missed, or a required function to fail with no workaround | Corrected before the level exits |
| Minor | A function fails with a workaround that does not affect acceptance | May be carried forward with an agreed correction date |
| Cosmetic | No effect on function or result | Corrected in the next scheduled release |

After Operational Acceptance, faults are handled under the support severities in System Architecture Section 12.4 rather than under this classification.

Correction and regression. Every correction is retested, and the tests its change could affect are repeated with it. A defect is closed when the retest passes, not when the correction is made. Every defect is logged with its class, cause, correction and retest result, and the log is delivered with the test reports.

Quality gates. Four contractual points are treated as quality gates, each with entry criteria and a recorded decision:

| Gate | Week | Entry criteria |
| --- | --- | --- |
| Detailed Design Approval | 6 | All design deliverables complete, reviewed with NRB and consistent with each other |
| Successful factory acceptance | 17 | Factory Acceptance Test report signed, no critical or major defect open |
| Installation Certificate | 26 | All pre-commissioning tests passed and their reports approved |
| Operational Acceptance | 30 | All operational acceptance tests passed, no critical unresolved defect |

Configuration control. Every tested build and configuration is versioned, and what passes acceptance is recorded as the baseline, so that what is deployed is what was tested. Changes after the baseline pass through the change control described in System Architecture Section 12.1.

Software quality. Software developed for this Contract is built under the secure development lifecycle and release gate described in System Architecture Section 10.5.

Quality assurance review. Test reports are reviewed and signed by the Supplier's quality assurance before they are submitted to NRB.

Documentation control. Every deliverable is versioned, reviewed and approved before issue, and delivered in editable format and as PDF.

Test deliverables. Factory Acceptance Test reports, the pre-commissioning reports listed in Section 4.5, User Acceptance Test reports, test scripts and results, performance test reports, stress test reports, security test reports, and defect logs with their resolutions.

# Warranty Defect Repair and Technical Support Service Sub-Plan

## Coverage and periods

| Obligation | Period | Basis |
| --- | --- | --- |
| Warranty defect repair | Three years from Final Acceptance | Technical Requirements 5.1.1.1, SCC GCC 29.4 |
| Spare parts supply | Three years from Operational Acceptance | SCC GCC 7.3 |
| Technical support: 24/7 hotline, Level 2 and Level 3 assistance | The warranty and post-warranty periods | Technical Requirements 5.2.1.1 and 5.2.1.2 |
| Post-warranty maintenance | Three years following the warranty period, renewable | Technical Requirements 5.2.1.3 |
| Post-Operational Acceptance technical assistance | From Operational Acceptance | Technical Requirements 5.3 |
| System availability of not less than 99 percent | The warranty and post-warranty periods | Measured as described in System Architecture Section 9.3 |

What the warranty covers. All equipment, systems, components, software and services supplied, installed, configured or commissioned under the Contract. The service covers diagnosis, repair, replacement, reconfiguration and restoration of defective items at no additional cost to the Purchaser. Warranty of the facility systems, including power, HVAC, fire suppression and physical security installations, is provided under the facility works.

Modes of service. Each class of component is serviced in the way that restores production fastest, and repair is kept off the critical path:

| Component | Mode | Restoration and repair |
| --- | --- | --- |
| Personalization and mailing equipment | On site | A faulty module is replaced from the on-site spares by the technical team. The faulty module is returned to the equipment manufacturer for repair and restocked |
| ICT infrastructure | On site | Services continue on the redundant components described in System Architecture Section 9.3 while the failed item is replaced from the on-site spares. The failed item is returned to its manufacturer under warranty |
| Hardware security modules | On site | If the module at the primary site fails, signing continues on the module at the secondary site, over the encrypted connection between the sites. A replacement module is enrolled from the remaining module, so no new key and no new certificate are needed |
| Application software | On call, remotely or on site | Defects are corrected and released under the change control described in System Architecture Section 12.1 |

## Support organization and service desk

Service delivery methodology. Every request for support follows one path. It is logged at the service desk with a reference, classified by severity, restored first and repaired second, escalated through the four support levels on the times in System Architecture Section 12.4, and closed only when its cause is recorded. A fault that recurs is taken to root cause analysis rather than repaired again, and the position is reported to NRB each month under Section 5.6.

Service desk. A user support hotline operates 24 hours a day, seven days a week. Every incident, whether reported by telephone, by email or through the service desk, is logged with a reference, a severity and an owner, and response time is counted from the moment it is logged.

Support levels. Four levels, defined in System Architecture Section 12.4:

| Level | Provided by |
| --- | --- |
| Level 1, first line | NRB operators and helpdesk staff trained under Section 3, supported by the technical team |
| Level 2, technical | The technical team at the Card Production Facility |
| Level 3, product line | The equipment manufacturer's product line specialists and the Supplier's senior engineers |
| Level 4, engineering | The equipment manufacturer's engineering and product development |

Technical team. The technical team required for post-Operational Acceptance technical assistance comprises the roles listed in System Architecture Section 12.4, each meeting the qualification and certification requirements for its role. The on-site attendance target for a critical incident is two hours at any hour of the day, so the team is based in Lilongwe.

Equipment manufacturer support. Level 3 and Level 4 support for the personalization and mailing equipment is provided by the equipment manufacturer under a support agreement with the Supplier covering the warranty period, so that escalation beyond the Supplier's own engineers reaches the people who designed the equipment.

Remote support and citizen data. Remote access for support is made only through the arrangement agreed with NRB and e-Government. It is used to diagnose, not to move data: citizen data is not stored or processed outside Malawi, as set out in System Architecture Section 10.2, and any log sent to a manufacturer for analysis has personal data removed before it leaves the facility.

Security incidents. An incident the service desk identifies as a security incident is handled under the classification and 24 hour notification described in System Architecture Section 10.7 rather than as an equipment fault.

Post-Operational Acceptance technical assistance. Modifications to the Information System after Operational Acceptance, such as those needed to comply with changes in legislation or regulation, are requested through the change procedure of the Contract and delivered under change control.

## Service levels and performance indicators

The service levels and performance indicators are set out in System Architecture Section 12.4: four severities with their response, on-site attendance and resolution targets, the escalation times between levels, and the targets for Overall Equipment Effectiveness, Mean Time To Repair, Mean Time Between Failures and Preventive Maintenance Compliance. They are not repeated here, so that there is one statement of each figure.

Service level commitment. We commit to those service levels and performance indicator targets for the warranty and post-warranty periods, and to the system availability of not less than 99 percent in Section 5.1, each measured as set out below and reported monthly.

How each measure is taken.

| Measure | Source and method |
| --- | --- |
| Response, attendance and resolution | Service desk records: the time an incident was logged, responded to, attended on site, restored and resolved |
| Overall Equipment Effectiveness | Production records: availability, multiplied by performance against the contractual rate in System Architecture Section 3.5, multiplied by the proportion of accepted cards |
| Mean Time To Repair | Service desk records, by severity |
| Mean Time Between Failures | Failure records for each critical equipment category, compared with the manufacturer's specified figure |
| Preventive Maintenance Compliance | Preventive maintenance tasks completed on schedule as a proportion of those scheduled, each month |
| Availability | Monitoring records, with the exclusions set out in System Architecture Section 9.3 |

Measures are drawn from the system's own records rather than compiled by hand, so that a figure in a service report can be traced to the events behind it.

## Preventive and corrective maintenance

Preventive maintenance. A preventive maintenance calendar is agreed with NRB at Operational Acceptance. The operating day is fourteen hours, so equipment maintenance is scheduled in the remaining hours and does not stop production.

| Activity | Frequency | Basis |
| --- | --- | --- |
| Servicing of the personalization and mailing equipment: optics, filtering system, feeders and card transport | At the equipment manufacturer's intervals | Manufacturer's maintenance schedule |
| Laser calibration | At the manufacturer's intervals and when calibration logs show drift | System Architecture Section 3.8 |
| Backup verification and restoration testing | On the backup schedule | System Architecture Section 12.3 |
| Security patching | On a defined cycle, with critical patches applied out of cycle | System Architecture Section 10.5 |
| Vulnerability assessment | At least quarterly | Technical Requirements 1.6.9 |
| Penetration testing | Annually, by an independent third party | Technical Requirements 1.6.9 |
| Disaster recovery test | At least annually | Technical Requirements 1.4.1.6 |
| Access recertification | At the interval set in the access control policy | Technical Requirements 1.6.4 |
| Certificate expiry monitoring | Continuous, with renewal raised at the agreed lead time | System Architecture Section 13.1 |

No scheduled preventive maintenance is deferred without the Purchaser's written approval, and compliance is reported monthly against the target in System Architecture Section 12.4.

Corrective maintenance. A fault is restored first and repaired second:

| Step | Action |
| --- | --- |
| Log | The incident is logged, classified by severity and assigned |
| Restore | Production is restored from the on-site spares or by failover, within the restoration target for its severity |
| Repair | The permanent correction is made, and a failed part is returned for repair |
| Replenish | The spare used is replaced within the replenishment time in System Architecture Section 12.5 |
| Review | A component failing more than twice in any 90 day period is subject to root cause analysis and a corrective action plan |

## Spare parts and consumables

The on-site holding, the replenishment times and the consumables stock are set out in System Architecture Section 12.5. The holding is delivered with the equipment and maintained at the Card Production Facility throughout the Contract period.

Critical Spare Parts List. Submitted to NRB for approval in week 24, before commissioning begins in week 27. For each item it states the minimum and maximum stock levels, the lead time, the equipment it applies to and the manufacturer's part number. It identifies every component that is a single point of failure, since each of those requires a replacement unit on site.

Spare parts by category.

| Category | Held for |
| --- | --- |
| Printer specific components | Laser marking units and their optics, the filtering system, card feeders and transport, verification cameras and reject modules, and the feeders, inserters and carrier printers of the mailing systems |
| Encoding and laminating modules | None are fitted. The cards are chipless, the QR code is laser engraved, and there is no laminating stage |
| Electronic and power spares | Industrial control PCs, power supplies, control boards and sensors of the equipment, and power supplies and drives of the ICT infrastructure |
| Infrastructure spares | A replacement for every critical infrastructure component identified as a single point of failure in the Critical Spare Parts List, and spare drives for the storage array. Components deployed in pairs, including the core switches, the firewalls, and the controllers and power supplies of the storage array, are covered by their second unit while a replacement is obtained, and the hardware security module at the primary site by the module at the secondary site. Spares for the facility systems are held under the facility works |
| Consumables and adjacent wear items | Lubricants, cleaning materials, filters, cleaning kits, fuses, belts, seals, gaskets, oils and greases, and calibration materials |

Spares are tracked like stock. The spares holding and the consumables are recorded in the stock control function described in System Architecture Section 6.10, with alerts against minimum levels, so that a spare used is visible for replenishment the moment it leaves the store.

## Service reporting, review and handover

Monthly service report. Each month the Supplier reports to NRB:

| Content | Detail |
| --- | --- |
| Incidents | Number by severity, with response, attendance and resolution against target |
| Performance indicators | Overall Equipment Effectiveness, Mean Time To Repair, Mean Time Between Failures and Preventive Maintenance Compliance |
| Availability | Achieved availability, with any excluded periods identified |
| Preventive maintenance | Tasks scheduled, completed and deferred with approval |
| Spare parts | Spares consumed and replenished, and holdings against minimum levels |
| Problems | Recurring failures, root cause analyses and corrective actions |
| Security | Security incidents notified in the period |

The report is reviewed with NRB each month, and any measure missing its target is reviewed with the action being taken to correct it.

Warranty and support documentation. Delivered at Operational Acceptance: warranty certificates, the support escalation matrix, the service level documents, and the equipment manufacturer's support contacts.

Handover of operation. From Operational Acceptance, NRB staff provide first-line support and operate the Security Operations Center, as described in System Architecture Section 10.7. The Supplier provides Level 2 support and above.

From warranty to post-warranty. At the end of the warranty period, support continues under post-warranty maintenance for three years, renewable, on the same response and resolution standards.

# Annex A. Licensing Bill of Materials

Every software license and subscription supplied under the Contract is listed below with its license metric, its quantity and the components it serves. Each is supplied with its entitlement, support and updates for three years from Operational Acceptance, so no title needs renewing within that period to remain licensed and supported.

Platform software.

| Title | License metric | Quantity | Serves |
| --- | --- | --- | --- |
| Windows Server Datacenter | Per physical core, with every core licensed and not fewer than 16 core licenses per host | All physical cores of the 5 hosts, 4 at the primary site and 1 at the secondary site | The server operating system and Hyper-V on every host, failover clustering of the application hosts and of the database hosts, and the Windows Server virtual machines those hosts run, including the domain controllers |
| Windows Server client access licenses | Per user | One for each person holding an account on the system | Access by users to the Windows Server estate |
| SQL Server Standard | Per virtual core, not fewer than four per virtual machine, with Software Assurance | The virtual cores allocated to the active database node | The production database. The passive node at the primary site and the secondary copy at the secondary site are covered by the failover rights of Software Assurance |
| SQL Server Developer | No license fee, for development and testing | The development, user acceptance testing and training environments | Non-production databases |
| Windows desktop operating system | Per device, supplied with the workstation | 10 | The operator and administrative workstations |
| Backup storage operating system | Per unit | 4, two at each site | The backup repository and the immutable backup storage at the primary and secondary sites |

Every host carries Windows Server Datacenter, because the edition licenses an unlimited number of Windows Server virtual machines on the host it covers. Either application host runs every production virtual machine of the application cluster when the other is lost, together with the non-production environments; the database hosts carry the clustered database; and the secondary host runs a domain controller, the secondary copy of the database and standby copies of the service virtual machines.

Security and operations software.

| Function | License metric | Quantity | Serves |
| --- | --- | --- | --- |
| Security information and event management | Event volume | The full event volume of the estate | Collection and correlation across all sources, and the Security Operations Center |
| Endpoint detection and response | Per endpoint | 35: the 5 hosts; 20 virtual machines, being the 16 production and 2 non-production virtual machines at the primary site, and the domain controller and the database copy at the secondary site; and the 10 workstations. The standby copies at the secondary site run only in place of the virtual machines they copy | Endpoint protection and anti-malware |
| Privileged access management | Per privileged user | Every administrator and privileged account | Privileged access issued for a session and a purpose |
| Multi-factor authentication | Per user | Every administrator and operator | Authentication of administrators and operators |
| Vulnerability scanning | Per scanned asset | All hosts, virtual machines, network devices and workstations | Scheduled vulnerability scanning and compliance reporting |
| Monitoring and log aggregation | Per monitored node | All infrastructure and application sources | Monitoring, alerting, ticket generation and log aggregation |
| Bulk SMS service | Per message, in a three-year bundle | The alert volume of the estate over three years | Delivery of alerts by SMS to the NRB staff designated for each type of alert |
| Backup and recovery, Veeam Backup & Replication | Per protected workload | 16, the production virtual machines at the primary site, with configuration and audit logs, replicated to the secondary site | Scheduled backup, immutable retention and restoration |
| Next generation firewall security subscriptions | Per appliance | 3: the high availability pair at the primary site and the firewall at the secondary site | Intrusion prevention signatures and threat updates |
| Storage array and network device support and firmware | Per device | The storage array, 5 switches and 2 firewalls at the primary site, and 1 switch and 1 firewall at the secondary site | Manufacturer support, replacement and firmware updates |
| Hardware security module support and client software | Per module | 2, one at each site | Firmware updates, and the client software through which the Signing Service reaches the modules |

Equipment software, supplied by the equipment manufacturer:

| Title | License metric | Quantity | Serves |
| --- | --- | --- | --- |
| Personalization control software | Per machine | 2 | Operation and marking control of the laser personalization systems |
| Mailing system control software | Per machine | 2 | Operation of the mailing and dispatch systems |
| Calibration and diagnostic software | Per machine | 4 | Laser calibration, and diagnostics for all four machines |
| Card layout template editor | Per installation | 1 | Card layout design on the workstation in the controlled design area |

Application software. The application services are custom software developed under the Contract: the Card Personalization Management System, Data Preparation Service, Signing Service, Printer Control Service, Quality Control Management, Mailing and Dispatch Management System, Stock Control and Card Accountability, Monitoring, Reporting and Analytics, and Administration and Access Control. The Purchaser holds the rights in them that the Contract grants in custom materials, and no license fee or subscription is needed to continue using them.

Components with no license fee. Open source components, including libraries, middleware and any software used for message queuing, are identified in the software inventory together with their license terms, as described in System Architecture Section 6.14.

Mapping of licenses to functional components.

| Functional component | Licenses it depends on |
| --- | --- |
| Card Personalization Management System | Windows Server Datacenter, SQL Server, client access licenses |
| Data Preparation Service and the NRIS interface | Windows Server Datacenter, SQL Server |
| Signing Service | Windows Server Datacenter, hardware security module client software |
| Printer Control Service | Windows Server Datacenter, personalization control software |
| Laser Personalization Control Software | Personalization control software, calibration and diagnostic software, card layout template editor |
| Quality Control Management | Windows Server Datacenter, SQL Server |
| Mailing and Dispatch Management System | Windows Server Datacenter, SQL Server, mailing system control software |
| Stock Control and Card Accountability | Windows Server Datacenter, SQL Server |
| Monitoring, Reporting and Analytics | Windows Server Datacenter, SQL Server, monitoring and log aggregation, bulk SMS service |
| Administration and Access Control | Windows Server Datacenter, client access licenses, multi-factor authentication, privileged access management |
| Security monitoring and the Security Operations Center | Security information and event management, endpoint detection and response, vulnerability scanning |
| Network and storage infrastructure | Next generation firewall security subscriptions, storage array and network device support and firmware |
| Backup, recovery and the secondary environment | Backup and recovery, Windows Server Datacenter, SQL Server |
| Operator and administrative workstations | Windows desktop operating system, endpoint detection and response, multi-factor authentication |

Three-year coverage.

| License type | Coverage for three years from Operational Acceptance |
| --- | --- |
| Windows Server and client access licenses | Perpetual licenses, with security and quality updates and support by the Supplier under Section 5 |
| SQL Server Standard | Perpetual licenses with Software Assurance for three years, providing updates, license mobility between the clustered hosts, and failover rights for the passive node and the secondary copy |
| Subscriptions: security, operations, firewall, storage array and network device support, and the bulk SMS service | A subscription term of three years |
| Equipment software | Support and updates from the equipment manufacturer for the warranty period |
| Hardware security modules | Support and firmware updates for three years |
| Application software | Corrected and updated under the warranty described in Section 5 |

License terms for every title are supplied with the Proposal in the Software List.